## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09404 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of KHANDAGHOSH Piped Water Supply Scheme under Burdwan Division, P.H.E. Dte._SL. No. 07 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000618/2021-2022 | 141/AE/HQ | 16/03/2022 | 26/03/2022 | MAKALI ENGINEERING CORPORATION | 4.52 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09404 | Augmentation | Augmentation of KHANDAGHOSH Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 600 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation & construction of boundary wall at Head works, 2nd TW & 3rd TW site under Khandaghosh Block, District - Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000017/2022-2023 | 1967/BWD | 12/04/2022 | 12/04/2023 | M/S JAN MAHAMMAD | 666.04 | 665.97 | 99.99 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09404 | Augmentation | Dismantling of concrete road for Augmentation of KHANDAGHOSH Pipe water supply scheme (Mouza: Khandaghosh, Lodna, Barisiali, Kapshit, Nabagram, Metedanga) at Khandaghosh Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000440/2022-2023 | 1466/BSD | 25/08/2022 | 09/10/2022 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 4.84 | 4.69 | 96.83 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09404 | Augmentation | Route Survey & Preparation of DPR for Khandaghosh W/S Scheme under Khandaghosh Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.15. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000504/2021-2022 | 190/BSD | 31/01/2022 | 02/03/2022 | RADIANT | 3.01 | 3.01 | 99.82 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09404 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2021-2022 | 565/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 25.72 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09404 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000205/2021-2022 | 1528/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09404 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000096/2021-2022 | 951/BWD | 17/02/2022 | 17/02/2022 | Resource Division | 59.29 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09404 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 3278/BWD | 29/07/2022 | 29/07/2022 | Resource Division | 34.57 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09404 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09404 | Augmentation | Providing Balance Functional Household Tap Connection (372 nos FHTC) from existing distribution system within the command area of KHANDAGHOSH Piped Water Supply Scheme at (Khandaghosh, Lodna, Metedanga, Nabagram, Kapsit, Barsiali) Mouza under KHANDAGHOSH Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000195/2023-2024 | 2689/BWD | 08/06/2023 | 08/07/2023 | KAUSHIK RAY | 16.73 | 0 | 0 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09404 | Augmentation | Construction of Boundary wall at Head Works Site of Aug. of KHANDAGHOSH Water Supply Scheme under KHANDAGHOSH Block of Burdwan Division, PHE Dte. (Length -210.00 Mtr, Col-80 Nos). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000534/2023-2024 | 3631/BWD | 21/08/2023 | 20/10/2023 | ROY ASSOCIATE | 28.73 | 28.7 | 99.89 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09404 | Augmentation | Restoration work of hard shoulder at Badulia Khandaghosh Road from 12.00 to 13.00 km (L/S) due to laying of water supply pipeline by PHE Dte. under Sadarghat Highway Sub-Division No.-I of Burdwan South Highway Division, P.W. Roads Dte. in the district of Purba Bardhaman. |  |  | BILL/00362/2024-2025 | 565/JJM | 23/07/2024 | 23/07/2024 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 8.12 | 0 | 0 | 0
Total | [13 empty] | 3856.94 | 702.36 | 18.21