## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SANKARI PWSS to accommodate FHTC in KHANDOGHOSH block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09405 | Augmentation | Route Survey & Preparation of DPR for Sankari W/S Scheme under Khandaghosh Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.10. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000498/2021-2022 | 185/BSD | 31/01/2022 | 02/03/2022 | RADIANT | 2.52 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SANKARI PWSS to accommodate FHTC in KHANDOGHOSH block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09405 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SANKARI PWSS to accommodate FHTC in KHANDOGHOSH block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09405 | Augmentation | Augmentation of SANKARI Piped Water Supply Scheme with LDS, Rising Main, Constn. of 250 cum capacity OHR with 20.0 Mtr. staging height inclusive of soil test & FHTC under Khandaghosh Block, District - Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000527/2021-2022 | 1119/BWD | 28/02/2022 | 28/02/2023 | UNIQUE AGENCY | 208.48 | 0 | 0 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SANKARI PWSS to accommodate FHTC in KHANDOGHOSH block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09405 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of SANKARI Piped Water Supply Scheme under Burdwan Division, P.H.E. Dte._SL No. 06 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000617/2021-2022 | 140/AE/HQ | 16/03/2022 | 26/03/2022 | MAKALI ENGINEERING CORPORATION | 4.52 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SANKARI PWSS to accommodate FHTC in KHANDOGHOSH block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09405 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000204/2021-2022 | 1527/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SANKARI PWSS to accommodate FHTC in KHANDOGHOSH block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09405 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000054/2021-2022 | 529/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 6.82 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SANKARI PWSS to accommodate FHTC in KHANDOGHOSH block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09405 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000093/2021-2022 | 903/BWD | 15/02/2022 | 15/02/2022 | Resource Division | 18.21 | 0 | 0 | 0
Total | [13 empty] | 3245.92 | 0 | 0