## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based BAHARAN-BIRHIMPUR PWSS to accommodate FHTC in Ketugram-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09406 | Augmentation | Route Survey and preparation of DPR for BAHARAN BIRHIMPUR PWSS under Ketugram-II Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-01] | Assistant Engineer |  | ORD/000537/2021-2022 | 43/KTS | 24/01/2022 | 14/02/2022 | RADIANT | 2.6 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based BAHARAN-BIRHIMPUR PWSS to accommodate FHTC in Ketugram-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09406 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based BAHARAN-BIRHIMPUR PWSS to accommodate FHTC in Ketugram-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09406 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000085/2021-2022 | 882/BWD | 11/02/2022 | 11/02/2022 | Resource Division | 7.08 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based BAHARAN-BIRHIMPUR PWSS to accommodate FHTC in Ketugram-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09406 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2021-2022 | 534/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 11.25 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based BAHARAN-BIRHIMPUR PWSS to accommodate FHTC in Ketugram-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09406 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000202/2021-2022 | 1525/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based BAHARAN-BIRHIMPUR PWSS to accommodate FHTC in Ketugram-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09406 | Augmentation | Augmentation of BAHRAN BIRAHIMPUR Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation with repairing of Pump house -I & II under Ketugram-II Block, District:- Purba-Burdwan. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000060/2022-2023 | 2252/BWD | 02/05/2022 | 02/05/2023 | ASHOK MITRA | 290.62 | 0 | 0 | 100
Total | [13 empty] | 3316.91 | 0 | 0