## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) | SM/09407 | Augmentation | Preparation of DPR for augmentation of Naopara W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-I) | Assistant Engineer |  | ORD/000576/2021-2022 | 211/KSD | 23/02/2022 | 16/03/2022 | ROY CHOWDHURY ASSOCIATES | 2.43 | 2.43 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) | SM/09407 | Augmentation | Laying Rising main and distribution pipeline including Providing Functional Household Tap Connection (FHTC) within the command are of Augmentation of NAOPARA Piped W/S. Scheme under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000003/2022-2023 | 1870/BWD | 05/04/2022 | 20/05/2022 | KOUSIK MALLICK | 66.6 | 66.49 | 99.84 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) | SM/09407 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) | SM/09407 | Augmentation | Work order for Repairing and laying of UPVC pipeline & providing FHTC work from Mallick oil mil to the house of Khalil Sk at Naopara Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000148/2023-2024 | 397/KSD | 02/05/2023 | 01/06/2023 | ARINDAM BHATTACHARYA | 0.99 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) | SM/09407 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Jahannagar, Ganganandapur, Nowapara & Monteswar Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, P.H.E. Dte.[Part ¿ A] | Assistant Engineer |  | ORD/000323/2022-2023 | 3632/BWD | 22/08/2022 | 11/09/2022 | RAMASISH ENTERPRISE | 12.8 | 3.2 | 25 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) | SM/09407 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2021-2022 | 542/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 9.97 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) | SM/09407 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000152/2021-2022 | 1240/BWD | 07/03/2022 | 07/03/2022 | Resource Division | 4.19 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) | SM/09407 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000203/2021-2022 | 1526/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) | SM/09407 | Augmentation | Work order for Repairing and laying of UPVC pipeline & providing FHTC work from wood shop to the house of Patal Das at Naopara Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000147/2023-2024 | 396/KSD | 02/05/2023 | 01/06/2023 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.99 | 0.69 | 69.66 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) | SM/09407 | Augmentation | Work Order for Repairing and laying of UPVC pipeline & providing FHTC work from the house of Habu Sk to the house of Asadul Kha at Naopara Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000127/2023-2024 | 421/KSD | 11/05/2023 | 10/06/2023 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.97 | 0.97 | 99.96 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) | SM/09407 | Augmentation | Work Order for "Repairing and laying of UPVC pipeline & providing FHTC work from the shop of Bhoton Sk to the petrol pump at Naopara Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." |  | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000553/2023-2024 | 1308/KSD | 23/08/2023 | 22/09/2023 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 3.59 | 3.58 | 99.81 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) | SM/09407 | Augmentation | Work Order for "Restoration of Pipeline of Naopara Piped Water Supply Scheme under Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl-1) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001131/2023-2024 | 2060/KSD | 23/02/2024 | 24/03/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 2.98 | 2.95 | 99.01 | 50
13 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) | SM/09407 | Augmentation | Work Order for "Road Restoration and other ancilliary works under NAOPARA(SM/09407) water supply scheme under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001191/2023-2024 | 2198/KSD | 15/03/2024 | 25/03/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 1.34 | 1.12 | 83.77 | 50
14 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) | SM/09407 | Augmentation | Work Order for "Ancillary work of Rising Main including Construction of Sluice Valve Chamber & other allied work of Naopara Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." (SL-2) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001132/2023-2024 | 2061/KSD | 23/02/2024 | 14/03/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 1.69 | 1.67 | 98.44 | 5
15 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) | SM/09407 | Augmentation | Quotation from WBSEDCL for load enhancement charges of Aug Naopara w/s scheme under Burdwan Division, PHE Dte. (Application No.-5004355150)(Ref. ID-500374861) |  |  | BILL/00903/2024-2025 | 1047/JJM | 30/10/2024 | 30/10/2024 | WBSEDCL | 1.34 | 0 | 0 | 0
Total | [13 empty] | 3115.24 | 83.09 | 2.67