## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman | SM/09408 | Augmentation | Augmentation of SEHARA Piped Water Supply Scheme with LDS, Rising Main, Construction of 350 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test & FHTC under Raina ¿ I Block, District - Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000599/2021-2022 | 1473/BWD | 14/03/2022 | 14/03/2023 | M/S PIONEER CONSTRUCTION | 430.73 | 394.99 | 91.7 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman | SM/09408 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of SEHARA & its adjoining mouzas Piped Water Supply Scheme, Block ¿ Raina ¿ I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000537/2022-2023 | 5025/BWD | 10/11/2022 | 10/12/2022 | M/S D. PALIT & CO. | 10.06 | 8.26 | 82.12 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman | SM/09408 | Augmentation | Route Survey & Preparation of DPR for Sehara W/S Scheme under Raina-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.9 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000497/2021-2022 | 184/BSD | 31/01/2022 | 02/03/2022 | RADIANT | 2.85 | 2.85 | 99.92 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman | SM/09408 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000212/2021-2022 | 1535/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman | SM/09408 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2021-2022 | 536/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 15.56 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman | SM/09408 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000091/2021-2022 | 902/BWD | 15/02/2022 | 15/02/2022 | Resource Division | 13.85 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman | SM/09408 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman | SM/09408 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at TubeWell Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17 (Size3.60mtr x 3.00mtr room) for SEHARA its Adjoining Mouza W/S Scheme, Block -Raina-I within Burdwan Sub-Division, PHE Dte. (Mouza- Sehara)_2ND CALL | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000576/2023-2024 | 2041/BSD | 24/08/2023 | 08/10/2023 | ANWESHA CONSTRUCTION | 3.21 | 2.87 | 89.35 | 100
Total | [13 empty] | 3481.63 | 408.97 | 11.75