## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL | SM/09409 | Augmentation | Preparation of DPR for augmentation of Samudragarh W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-E) | Assistant Engineer |  | ORD/000583/2021-2022 | 217/KSD | 24/02/2022 | 17/03/2022 | M/S R. DUTTA & CO. | 2.8 | 2.78 | 99.59 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL | SM/09409 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of SAMUDRAGARH Piped Water Supply Scheme under Burdwan Division, P.H.E. Dte.SL. No. 10 | Assistant Engineer |  | ORD/000636/2021-2022 | 144/AE/HQ | 16/03/2022 | 26/03/2022 | MA SARADA ENTERPRISE | 4.52 | 4.52 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL | SM/09409 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL | SM/09409 | Augmentation | Additional works to implement the augmentation of SAMUDRAGARH Piped Water Supply Scheme under Purbasthali-I Block, Dist :- Purba Burdwan under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000016/2023-2024 | 1731/BWD | 13/04/2023 | 13/05/2023 | AZAD CONSTRUCTION | 18.67 | 15.24 | 81.62 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL | SM/09409 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000109/2021-2022 | 930/BWD | 16/02/2022 | 16/02/2022 | Resource Division | 22 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL | SM/09409 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000208/2021-2022 | 1531/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL | SM/09409 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2021-2022 | 540/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 20.81 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL | SM/09409 | Augmentation | Quotation charges of WBSEDCL of Aug. of Samudragarh PWSS. [Ref. ID-503495985] |  |  | BILL/01124/2023-2024 | 1087/JJM | 20/12/2023 | 20/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.42 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL | SM/09409 | Augmentation | Augmentation of SAMUDRAGARH Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 450 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation including with construction of boundary wall at Head works site under Purbasthali I Block, District - Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000015/2022-2023 | 1963/BWD | 12/04/2022 | 12/04/2023 | AZAD ENTERPRISE | 426.18 | 262.64 | 61.63 | 80
10 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL | SM/09409 | Augmentation | Quotation charges of WBSEDCL of Aug. of Samudragarh PWSS. [Ref. ID-503564676][TW-4] |  |  | BILL/01690/2023-2024 | 1366/JJM | 20/02/2024 | 20/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.35 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL | SM/09409 | Augmentation | Quotation from WBSEDCL for load enhancement of Augmentation of Samudragarh w/s scheme for P.H.-3 under Burdwan Division, PHE Dte. |  |  | BILL/01928/2023-2024 | 1825/JJM | 27/03/2024 | 27/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.39 | 0 | 0 | 0
Total | [13 empty] | 3512.51 | 285.19 | 8.12