## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District | SM/09410 | Augmentation | Sinking of additional 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SINHARI Piped Water Supply Scheme, Block - Purbasthali - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000071/2022-2023 | 2425/BWD | 11/05/2022 | 10/06/2022 | M/S SYCHROTECH INDUSTRY | 9.01 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District | SM/09410 | Augmentation | Preparation of DPR for augmentation of Sinhari W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-C) | Assistant Engineer |  | ORD/000581/2021-2022 | 215/KSD | 24/02/2022 | 17/03/2022 | LEMNISCATE | 2.92 | 2.86 | 98.11 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District | SM/09410 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District | SM/09410 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1,2 &3 at Augumentation of Sinhari Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000078/2023-2024 | 2574/CMD | 06/06/2023 | 06/07/2023 | P.K. ENGINEERING | 33.08 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District | SM/09410 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2021-2022 | 539/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 16.89 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District | SM/09410 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000161/2021-2022 | 1321/BWD | 08/03/2022 | 08/03/2022 | Resource Division | 44.3 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District | SM/09410 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000213/2021-2022 | 1536/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District | SM/09410 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000153/2021-2022 | 1241/BWD | 07/03/2022 | 07/03/2022 | Resource Division | 4.19 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District | SM/09410 | Augmentation | Augmentation of SINHARI Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 350 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation including construction of switch room (3.60mx3.0m) for new TW site under Purbasthali II Block, District - Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000010/2022-2023 | 1940/BWD | 11/04/2022 | 11/04/2023 | CONCORD ENGINEERING | 441.1 | 292.72 | 66.36 | 60
10 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District | SM/09410 | Augmentation | Different types of works involve in connection with Augmentation of KRISHNABATI (SM/07827), PURBASTHLI (SM/07866), SINHARI (SM/09716) & SURFACE based W/S Scheme (SM/15571) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000181/2024-2025 | 2296/BWD | 20/06/2024 | 26/02/2026 | M/S DATTA ENTERPRISE | 579.85 | 40.37 | 6.96 | 2
Total | [13 empty] | 4136.7 | 335.96 | 8.12