## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Interconnection of rising main from 2nd Tube Well site and renovation of boundary wall and pump house at 2nd Tube Well Site of Ganganandapur W/S Scheme within Kalna Sub-Division under Burdwan Division , PHE Dte. (Sl No-C) | Assistant Engineer |  | ORD/000449/2021-2022 | 88/KSD | 21/01/2022 | 20/02/2022 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 1.2 | 0.86 | 72.03 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Preparation of DPR for augmentation of Ganganandapur W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-E) | Assistant Engineer |  | ORD/000571/2021-2022 | 207/KSD | 23/02/2022 | 16/03/2022 | ROY CHOWDHURY ASSOCIATES | 2.84 | 2.82 | 99.34 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Sinking of additional 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for GANGANANDAPUR Piped Water Supply Scheme, Block - Purbasthali - I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000070/2022-2023 | 2424/BWD | 11/05/2022 | 10/06/2022 | M/S SYCHROTECH INDUSTRY | 9.01 | 8.47 | 94.03 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Construction of Pump House cum switch room (5.40 mtr x 3.60 mtr) with sanitary arrangement (as per drawing no. PHE/SE/CC/PH/DWG-01/2022-2023) at GANGANANDAPUR Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE Dte. Dist.-Purba Bardhaman. |  |  | ORD/000708/2023-2024 | 4481/BWD | 11/10/2023 | 10/12/2023 | LOKNATH ENTERPRISE | 6.31 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Jahannagar, Ganganandapur, Nowapara & Monteswar Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, P.H.E. Dte.[Part ¿ A] | Assistant Engineer |  | ORD/000323/2022-2023 | 3632/BWD | 22/08/2022 | 11/09/2022 | RAMASISH ENTERPRISE | 12.8 | 3.2 | 25 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000081/2021-2022 | 603/BWD | 28/01/2022 | 28/01/2022 | Resource Division | 24.12 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2021-2022 | 553/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 18.08 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000201/2021-2022 | 1524/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000105/2021-2022 | 952/BWD | 17/02/2022 | 17/02/2022 | Resource Division | 74.99 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2022-2023 | 4626/BWD | 17/10/2022 | 17/10/2022 | Resource Division | 18.48 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Quotation from WBSEDCL for new service connection of Ganganandapur w/s scheme. T.W.-3 |  |  | BILL/00401/2023-2024 | 537/JJM | 21/08/2023 | 21/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.6 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Ganganandapur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000073/2023-2024 | 2562/CMD | 06/06/2023 | 06/07/2023 | SUDIPTA GHOSH | 10.98 | 10.45 | 95.11 | 95
14 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Additional works to implement the GANGANANDAPUR Piped Water Supply Scheme under Purbasthali-I Block, Dist :- Purba Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000707/2022-2023 | 754/BWD | 23/02/2023 | 24/04/2023 | MANASH GHOSH | 76.57 | 76.42 | 99.8 | 85
15 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 14 Nos. Piped W/S. Schemes under Purbasthali I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000337/2024-2025 | 3017/BWD | 05/08/2024 | 19/10/2024 | HORIZEN | 38 | 16.76 | 44.1 | 100
16 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Work Order for " Renovation of Pump house along with laboratory building of Ganganandapur piped water supply scheme in connection with Augmentation of Ganganandapur Piped Water Supply Scheme under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000135/2024-2025 | 318/KSD | 07/06/2024 | 07/07/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 4.31 | 4.24 | 98.46 | 100
17 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Work Order for "Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory under The Assistant Engineer, Kalna Sub- Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation,Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL : Ganganandapur Sub District Water Testing Laboratory under Kalna Sub Division)". | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE,JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000671/2023-2024 | 1334/KSD | 28/08/2023 | 27/09/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.51 | 0 | 0 | 1
18 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Work Order for " Renovation of boundary wall in connection with Augmentation of Ganganandapur Water Supply Scheme (SM/09411) within Kalna Sub-Division under Burdwan Division, PHE Dte. (Length - 170 Mtr). - 2 Nos". | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000801/2024-2025 | 1778/KSD | 20/11/2024 | 20/12/2024 | UNIQUE CONSTRUCTION | 4.55 | 0 | 0 | 100
19 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Renovation of Pump House in connection with Augmentation of Ganganandapur piped Water supply (SM/09411) Scheme under Kalna Sub-Division under Burdwan Division, PHE Dte. (2 Nos Pump House Repairing) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000748/2024-2025 | 3748/BWD | 29/10/2024 | 28/11/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 9.7 | 0.25 | 2.61 | 100
20 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Work order for "Construction of Toilet (1.8 m x 1.8 m) with saitary arrangement along with other allied works at PH No-3 of Ganganandapur pwss (SM/09411) under Kalna sub division under Burdwan Division.". | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001321/2024-2025 | 303/KSD | 25/02/2025 | 27/03/2025 | DUTTA CONSTRUCTION & CONSULTANCY | 2.45 | 0 | 0 | 100
21 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Augmentation of GANGANANDAPUR Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 300 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation & construction of pump house ( 3.60mx 3.0m) & boundary wall at new TW site under Purbasthali ¿ I Block, District - Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000019/2022-2023 | 2013/BWD | 18/04/2022 | 01/02/2025 | MANASH GHOSH | 421.4 | 377.79 | 89.65 | 70
22 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Work Order for "Additional work in connection with renovation of Pump house and laboratory building of Ganganandapur piped water supply scheme in connection with Augmentation of Ganganandapur Piped Water Supply Scheme under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000136/2024-2025 | 319/KSD | 07/06/2024 | 07/07/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 3.83 | 0 | 0 | 100
23 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. | SM/09411 | Augmentation | Laying of rising main along with crossing of pipeline by HDD/Jack pushing method with other allied work in connection with augmentation of Ganganandapur PWSS (SM/09411) & Rajapur PWSS (SM/ 14021), Purbasthali-I block under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000278/2024-2025 | 2710/BWD | 11/07/2024 | 16/10/2025 | MANASH GHOSH | 81.34 | 0 | 0 | 60
Total | [13 empty] | 3833.43 | 501.27 | 13.08