## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09413 | Augmentation | Route Survey and preparation of DPR for PALITA PWSS under Ketugram-I Block under Katwa Sub-Division under Burdwan Division PHE Dte.[Sl No-04] | Assistant Engineer |  | ORD/000540/2021-2022 | 55/KTS | 25/01/2022 | 15/02/2022 | RADIANT | 2.78 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09413 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09413 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of PALITA Piped Water Supply Scheme under Burdwan Division, P.H.E. Dte._Sl. No. 09 | Assistant Engineer |  | ORD/000620/2021-2022 | 143/AE/HQ | 16/03/2022 | 26/03/2022 | MAKALI ENGINEERING CORPORATION | 4.52 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09413 | Augmentation | Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day.(Sl No-1) |  |  | ORD/000510/2023-2024 | 499/KTS | 22/05/2023 | 31/07/2023 | M/S MUNMUN DEY | 0.9 | 0 | 0 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09413 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2021-2022 | 543/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 15.49 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09413 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000207/2021-2022 | 1530/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09413 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000107/2021-2022 | 929/BWD | 16/02/2022 | 16/02/2022 | Resource Division | 26.89 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09413 | Augmentation | Augmentation of PALITA Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 350 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation, Construction of boundarywall at HW and 2nd TW site with repairing of Pump house -I & II under Ketugram-I Block, District:- Purba-Burdwan. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000029/2022-2023 | 2139/BWD | 25/04/2022 | 01/01/2026 | M/S GUPTA ENTERPRISE | 472.81 | 0 | 0 | 98
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09413 | Augmentation | Continuation order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day. (Sl No-1) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000930/2023-2024 | 1016/KTS | 20/09/2023 | 13/10/2023 | M/S MUNMUN DEY | 0.3 | 0 | 0 | 0
Total | [13 empty] | 3529.05 | 0 | 0