## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of MANTESWAR PWSS for providing functional household tap connection FHTC in Manteswar block under Burdwan Division in Purba Bardhaman District | SM/09414 | Augmentation | Preparation of DPR for augmentation of Monteswar W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-F) | Assistant Engineer |  | ORD/000572/2021-2022 | 208/KSD | 23/02/2022 | 16/03/2022 | INDRANIL DUTTA & ASSOCIATES | 2.75 | 2.73 | 99.07 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of MANTESWAR PWSS for providing functional household tap connection FHTC in Manteswar block under Burdwan Division in Purba Bardhaman District | SM/09414 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Jahannagar, Ganganandapur, Nowapara & Monteswar Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, P.H.E. Dte.[Part B] | Assistant Engineer |  | ORD/000357/2022-2023 | 3728/BWD | 30/08/2022 | 19/09/2022 | NANDY UDYOG | 2.88 | 2.88 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of MANTESWAR PWSS for providing functional household tap connection FHTC in Manteswar block under Burdwan Division in Purba Bardhaman District | SM/09414 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of MANTESWAR PWSS for providing functional household tap connection FHTC in Manteswar block under Burdwan Division in Purba Bardhaman District | SM/09414 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Jahannagar, Ganganandapur, Nowapara & Monteswar Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, P.H.E. Dte.[Part ¿ A] | Assistant Engineer |  | ORD/000323/2022-2023 | 3632/BWD | 22/08/2022 | 11/09/2022 | RAMASISH ENTERPRISE | 12.8 | 3.2 | 25 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of MANTESWAR PWSS for providing functional household tap connection FHTC in Manteswar block under Burdwan Division in Purba Bardhaman District | SM/09414 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for 1ST TW Site of Aug. of MONTESWAR & its adjoining mouzas Piped Water Supply Scheme, Block ? Monteswar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000550/2022-2023 | 5178/BWD | 23/11/2022 | 23/12/2022 | ANIRUDDHA FARUQUE | 8.73 | 0 | 0 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of MANTESWAR PWSS for providing functional household tap connection FHTC in Manteswar block under Burdwan Division in Purba Bardhaman District | SM/09414 | Augmentation | Work Order for "Surging of existing 300 x 200 mm dia Tube Well depth 123 mtr & lowering of part tube well 200 x 150 mm dia depth , existing 300 x 200 mm dia tube well at Manteswar zone-I under Kalna Sub-Division , PHE Dte." |  | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000551/2023-2024 | 1306/KSD | 23/08/2023 | 22/09/2023 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 4.2 | 0 | 0 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of MANTESWAR PWSS for providing functional household tap connection FHTC in Manteswar block under Burdwan Division in Purba Bardhaman District | SM/09414 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2021-2022 | 563/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 14.37 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of MANTESWAR PWSS for providing functional household tap connection FHTC in Manteswar block under Burdwan Division in Purba Bardhaman District | SM/09414 | Augmentation | Quotation for new service connection charges of Monteswar PWSS.[PH No.-3] |  |  | BILL/01126/2023-2024 | 1085/JJM | 20/12/2023 | 20/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.99 | 0 | 0 | 0
Total | [13 empty] | 3055.73 | 8.81 | 0.29