## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL | SM/09415 | Augmentation | Preparation of DPR for augmentation of Dogachia W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-H) | Assistant Engineer |  | ORD/000574/2021-2022 | 210/KSD | 23/02/2022 | 16/03/2022 | ROY CHOWDHURY ASSOCIATES | 2.62 | 2.65 | 101.15 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL | SM/09415 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL | SM/09415 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of DOGACHIA Piped Water Supply Scheme under Burdwan Division, P.H.E. Dte._SL.No-08 | Assistant Engineer |  | ORD/000619/2021-2022 | 142/AE/HQ | 16/03/2022 | 26/03/2022 | MAKALI ENGINEERING CORPORATION | 4.52 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL | SM/09415 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for 2nd TW Site of Aug. of DOGACHHIA & its adjoining mouzas Piped Water Supply Scheme, Block ? Purbasthali ? I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000547/2022-2023 | 5129/BWD | 21/11/2022 | 21/12/2022 | MUNSHI ENTERPRISE | 8.72 | 7.89 | 90.47 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL | SM/09415 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000149/2021-2022 | 1247/BWD | 07/03/2022 | 07/03/2022 | Resource Division | 4.19 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL | SM/09415 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2021-2022 | 541/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 9.17 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL | SM/09415 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000206/2021-2022 | 1529/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL | SM/09415 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000104/2021-2022 | 949/BWD | 17/02/2022 | 17/02/2022 | Resource Division | 14.44 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL | SM/09415 | Augmentation | Sinking of tube well, laying dist. system, construction of pump house and laying rising main of DOGACHIA Piped Water Supply Scheme with Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000877/2023-2024 | 5337/BWD | 04/12/2023 | 02/04/2024 | MITRA CONSTRUCTION | 78.72 | 15.34 | 19.48 | 20
10 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL | SM/09415 | Augmentation | Additional work to implement augmentation of DOGACHHIA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000929/2023-2024 | 5512/BWD | 14/12/2023 | 13/01/2024 | PARTHA PRATIM ACHARYA | 9.39 | 6.22 | 66.21 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL | SM/09415 | Augmentation | Quotation from WBSEDCL for Augmentation of Dogachia water supply scheme for Pump House No.-4 under Burdwan Division, PHE Dte. |  |  | BILL/00365/2024-2025 | 566/JJM | 23/07/2024 | 23/07/2024 | WBSEDCL | 8.89 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL | SM/09415 | Augmentation | Quotation from WBSEDCL for Augmentation of Dogachia water supply scheme for Pump House No.-3 under Burdwan Division, PHE Dte. |  |  | BILL/00366/2024-2025 | 567/JJM | 23/07/2024 | 23/07/2024 | WBSEDCL | 7.63 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL | SM/09415 | Augmentation | Augmentation of DOGACHIA Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 200 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation & boundary wall construction at 2nd TW site under Purbasthali ¿ I Block, District - Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000678/2021-2022 | 1809/BWD | 31/03/2022 | 31/03/2023 | MITRA CONSTRUCTION | 226.14 | 186.35 | 82.41 | 60
Total | [13 empty] | 3379.8 | 218.45 | 6.46