## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District | SM/09416 | Augmentation | Preparation of DPR for augmentation of Champahati W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-G) | Assistant Engineer |  | ORD/000573/2021-2022 | 209/KSD | 23/02/2022 | 16/03/2022 | INDRANIL DUTTA & ASSOCIATES | 2.7 | 2.71 | 100.18 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District | SM/09416 | Augmentation | Relaying of HDPE pipeline at damaged portion at Kutirpara village within Champahati W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-A) | Assistant Engineer |  | ORD/000469/2021-2022 | 152/KSD | 15/02/2022 | 17/03/2022 | P.C. CONSTRUCTION | 4.84 | 4.85 | 100.14 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District | SM/09416 | Augmentation | Augmentation of CHAMPAHATI Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 250 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test with construction of boundary wall at Head works site under Kalna ¿ II Block, District - Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000653/2021-2022 | 1655/BWD | 22/03/2022 | 22/03/2023 | MONDAL ENTERPRISE | 265.13 | 263.45 | 99.37 | 80
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District | SM/09416 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2021-2022 | 564/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 10.64 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District | SM/09416 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000211/2021-2022 | 1534/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District | SM/09416 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000103/2021-2022 | 950/BWD | 17/02/2022 | 17/02/2022 | Resource Division | 35.32 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District | SM/09416 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000084/2021-2022 | 606/BWD | 28/01/2022 | 28/01/2022 | Resource Division | 24.12 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District | SM/09416 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2022-2023 | 4633/BWD | 17/10/2022 | 17/10/2022 | Resource Division | 12.32 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District | SM/09416 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District | SM/09416 | Augmentation | Additional works to implement the CHAMPAHATI Piped Water Supply Scheme under Purbasthali-I Block, Dist :- Purba Burdwan under Burdwan Divn., PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000757/2022-2023 | 1270/BWD | 17/03/2023 | 16/04/2023 | MONDAL ENTERPRISE | 24.02 | 23.59 | 98.23 | 50
11 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District | SM/09416 | Augmentation | Additional works for construction of OHR having capacity 250 cum in connection with Augmentation of CHAMPAHATI PWSS (SM/09416) under Purbasthali-I Block under Kalna Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000359/2024-2025 | 2924/BWD | 26/07/2024 | 24/10/2024 | MONDAL ENTERPRISE | 27.44 | 0 | 0 | 2
12 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District | SM/09416 | Augmentation | Work Order for "Laying of Rising Main for CHAMPAHATI(SM/09416) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001184/2023-2024 | 2187/KSD | 15/03/2024 | 25/03/2024 | DEL DELTA CONSTRUCTION | 4.82 | 0 | 0 | 2
13 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District | SM/09416 | Augmentation | Additional Work of CHAMPAHATI Piped Water Supply Scheme with sinking of Tube-wells, LDSs, FHTCs, construction of switch rooms & boundary wall with gate under PURBASTHALI-I Block, District:- Purba Bardhaman._2ND CALL. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001011/2023-2024 | 370/BWD | 29/01/2024 | 30/09/2024 | ANWESHA CONSTRUCTION | 59.07 | 50.44 | 85.39 | 20
Total | [13 empty] | 3475.79 | 345.04 | 9.93