## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SRIDHARPUR PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09488 | Augmentation | Route Survey & Preparation of DPR for Sridharpur W/S Scheme under Memari-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.6. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000494/2021-2022 | 181/BSD | 31/01/2022 | 02/03/2022 | RADIANT | 2.59 | 2.59 | 99.99 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SRIDHARPUR PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09488 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SRIDHARPUR PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09488 | Augmentation | Augmentation of SRIDHARPUR Piped Water Supply Scheme with LDS, FHTC, Rising Main with necessary interconnection, Construction of 200 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation under Memari II Block, District Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000007/2022-2023 | 1937/BWD | 11/04/2022 | 11/04/2023 | SUJAY KUMAR RAY | 251.3 | 178.78 | 71.14 | 60
4 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SRIDHARPUR PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09488 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000062/2021-2022 | 562/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 11 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SRIDHARPUR PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09488 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000110/2021-2022 | 1069/BWD | 24/02/2022 | 24/02/2022 | Resource Division | 37.52 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SRIDHARPUR PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09488 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000197/2021-2022 | 1520/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SRIDHARPUR PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09488 | Augmentation | Replacement of Tube-well & Rising main at HEAD TW site for Aug. of PARHATI, SRIDHARPUR, SATGACHIA ZONE-I, SATGACHIA ZONE-II, Piped Water Supply Scheme within MEMARI-II Block under Burdwan Divn., PHE. Dte. District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000973/2023-2024 | 24/BWD | 03/01/2024 | 01/10/2025 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 54.2 | 17.35 | 32 | 90
Total | [13 empty] | 3361.98 | 198.72 | 5.91