## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09489 | Augmentation | Route Survey & Preparation of DPR for Nababhat W/S Scheme under Burdwan-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl. No.14. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000503/2021-2022 | 189/BSD | 31/01/2022 | 02/03/2022 | RADIANT | 2.87 | 2.86 | 99.61 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09489 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09489 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of NABABHAT & its adjoining mouzas Piped Water Supply Scheme, Block - Burdwan - I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000552/2022-2023 | 5194/BWD | 24/11/2022 | 24/12/2022 | ANIRUDDHA FARUQUE | 11.24 | 9.61 | 85.49 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09489 | Augmentation | Construction of boundary wall at East side of Nababhat PHE Complex Burdwan Division, PHE Dte. (Length-106.0Mtr, Col-37 Nos.) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000431/2021-2022 | 4664/BWD | 10/09/2021 | 10/10/2021 | MANAS KUMAR CHATTERJEE | 7.89 | 8.03 | 101.85 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09489 | Augmentation | Land Development at East Side of Office Building under Nababhat PHE Complex under Burdwan Sub-Division in Burdwan Division,PHE Dte. Gr.D. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000466/2021-2022 | 277/BSD | 15/02/2022 | 17/03/2022 | MANAS KUMAR CHATTERJEE | 3.17 | 3.17 | 99.81 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09489 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Paharhati, Nababhat, Shyamsundar & Dewandighi-Mirzapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000519/2022-2023 | 4703/BWD | 19/10/2022 | 08/11/2022 | SSPR VALVE MANUFACTURING PVT LTD. | 14.45 | 3.61 | 25 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09489 | Augmentation | Wall Painting at East Side Boundary Wall of Nababhat PHE Complex for IEC Programme for FHTC WORK under Burdwan Sub-Division, PHE Dte. Gr. A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000507/2022-2023 | 1067/BSD | 27/06/2022 | 04/07/2022 | FIVE HURDS ENGINEERING FARM | 0.4 | 0.39 | 97.71 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09489 | Augmentation | Construction of boundary wall (with main gate) at west side of Nababhat PHE complex of Augmentation of Nababhat under Burdwan Division, PHE Dte. (Length-110 Mtr, Col-45 Nos.) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000935/2021-2022 | 6254/BWD | 01/11/2021 | 01/12/2021 | SUROVI CONSTRUCTION AND GENERAL ORDER SUPPLIERS | 7.05 | 6.59 | 93.56 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09489 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000162/2021-2022 | 1322/BWD | 08/03/2022 | 08/03/2022 | Resource Division | 12.13 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09489 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000155/2021-2022 | 1238/BWD | 07/03/2022 | 07/03/2022 | Resource Division | 4.19 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09489 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000061/2021-2022 | 544/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 25.82 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09489 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000214/2021-2022 | 1537/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09489 | Augmentation | Augmentation of NABABHAT Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 450 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation & repairing of Pump House at Head works & 2nd TW site under Burdwan I Block, District - Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000016/2022-2023 | 1964/BWD | 12/04/2022 | 01/04/2025 | S.P. CONSTRUCTION | 514.15 | 442.02 | 85.97 | 100
Total | [13 empty] | 3608.73 | 476.28 | 13.2