## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09492 | Augmentation | Route Survey & Preparation of DPR for Sagrai W/S Scheme under Khandaghosh Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.11. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000500/2021-2022 | 186/BSD | 31/01/2022 | 02/03/2022 | RADIANT | 2.92 | 2.91 | 99.58 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09492 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09492 | Augmentation | Repairing of dismantling concrete road by Cement Concrete (1:3:6) for Augmentation of KHANDAGHOSH Pipe Water Supply Scheme (Mouza Khandaghosh, Iodna, Barisiali, Kapshit, Nabagram, Metedanga) at Khandaghosh Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000364/2022-2023 | 1403/BSD | 10/08/2022 | 09/10/2022 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 4.81 | 0 | 0 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09492 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for Augmentation of SAGRAI & its adjoining mouzas Piped Water Supply Scheme, Block - Khandaghosh, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000516/2022-2023 | 4613/BWD | 17/10/2022 | 16/11/2022 | M/S SYCHROTECH INDUSTRY | 10.22 | 8.15 | 79.72 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09492 | Augmentation | Augmentation of SAGRAI Piped Water Supply Scheme with LDS, FHTC, Rising Main with necessary interconnections & Construction of 400 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test under Khandaghosh Block, District - Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000642/2021-2022 | 1624/BWD | 21/03/2022 | 02/04/2022 | NATIONAL CONSTRUCTION | 472.26 | 472.14 | 99.97 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09492 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000058/2021-2022 | 561/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 16.61 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09492 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000218/2021-2022 | 1541/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09492 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000092/2021-2022 | 931/BWD | 16/02/2022 | 16/02/2022 | Resource Division | 25.87 | 0 | 0 | 0
Total | [13 empty] | 3538.07 | 483.2 | 13.66