## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09495 | Augmentation | Route Survey & Preparation of DPR for Shyamsundar W/S Scheme under Raina-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.7. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000495/2021-2022 | 182/BSD | 31/01/2022 | 02/03/2022 | RADIANT | 2.9 | 2.89 | 99.59 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09495 | Augmentation | Supply of 100 mm dia C.I. Sluice valve(P.N.-I) of Augmentation of Shyamsundar Water Supply Scheme of Raina-I under Burdwan Sub Division, PHE Dte. Gr.F. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000479/2022-2023 | 1603/BSD | 14/09/2022 | 29/09/2022 | SK ALIM | 1.73 | 1.73 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09495 | Augmentation | Extension of Pipeline for Shyamsundar village Uttar para of Augmentation of Shyamsundar Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.G. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000480/2022-2023 | 1604/BSD | 14/09/2022 | 14/10/2022 | M/S PROCHESTA ENTERPRISE | 4.78 | 4.77 | 99.86 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09495 | Augmentation | Extension of Pipeline for Shyamsundar village Dakshin para of Augmentation of Shyamsundar Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.I. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000482/2022-2023 | 1606/BSD | 14/09/2022 | 14/10/2022 | SK ABDUL HALIM | 4.77 | 4.77 | 100 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09495 | Augmentation | Concrete cutting of khalina, shibrampur, shyamsundar uttar para,shyamsundar dakshin para ,natungram village for Augmentation of Shyamsundar Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.D. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000367/2022-2023 | 1406/BSD | 10/08/2022 | 09/09/2022 | SK ALIM | 4.68 | 4.68 | 99.87 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09495 | Augmentation | Extension of Pipeline for Natungram and Shyamsundar village of Augmentation of Shyamsundar Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.C | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000441/2022-2023 | 1479/BSD | 25/08/2022 | 09/10/2022 | SK ABDUL HALIM | 4.84 | 4.83 | 99.93 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09495 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09495 | Augmentation | Conversion of ACSR Cond to AB CABL of 11KV Shyamsundar Feeder Emanating from Raina S/STN at Shyamsundar PWSS under Burdwan Division, PHE Dte. [Ref ID-860250397, Application ID-100000060727, dt.-16/09/2022] |  |  | VCH/000551/2022-2023 | 653/DW/22-23 | 28/09/2022 | 28/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.08 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09495 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Paharhati, Nababhat, Shyamsundar & Dewandighi-Mirzapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000519/2022-2023 | 4703/BWD | 19/10/2022 | 08/11/2022 | SSPR VALVE MANUFACTURING PVT LTD. | 14.45 | 3.61 | 25 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09495 | Augmentation | Sand filling at PWD road side near bazar to thana more(Drawing NOD 15 to 16,16 to 17,6 to 89,11 to 12,12 to 13,12 to 156,10 to 11,13 to 14,14 to 15,1 to 2 to 267,2 to 3 ,7 to 8,7 to 82,4 to 5 ,5 to 6,6 to 82,3 to 4. at Shyamsundar Water supply scheme of Raina Block within Burdwan Division, PHE Dte. Gr.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000501/2022-2023 | 1224/BSD | 08/07/2022 | 15/07/2022 | SK ALIM | 4.16 | 4.09 | 98.31 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09495 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for Augmentation of SHYAMSUNDAR & its adjoining mouzas Piped Water Supply Scheme [Shyamsundar Mouza], Block ¿ Raina ¿ I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000509/2022-2023 | 4446/BWD | 27/09/2022 | 27/10/2022 | SK ALIM | 9.87 | 8.55 | 86.64 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09495 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2021-2022 | 532/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 15.09 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09495 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000089/2021-2022 | 901/BWD | 15/02/2022 | 15/02/2022 | Resource Division | 23.47 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09495 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000216/2021-2022 | 1539/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
15 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/09495 | Augmentation | Augmentation of SHYAMSUNDAR Piped Water Supply Scheme with LDS, Rising Main, Construction of 350 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test, Construction of boundary wall at Head works & 2nd TW site & FHTC under Raina ¿ I Block, District - Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000598/2021-2022 | 1474/BWD | 14/03/2022 | 14/03/2023 | SK ALIM | 474.78 | 412.65 | 86.91 | 100
Total | [13 empty] | 3571.95 | 452.57 | 12.67