## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Route Survey and preparation of DPR for MAJHIGRAM-SINGHOT PWSS under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-05] | Assistant Engineer |  | ORD/000546/2021-2022 | 56/KTS | 25/01/2022 | 15/02/2022 | RADIANT | 2.63 | 2.63 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Head Work Site to departmental drawing (Size 3.60 mtr x 3.00 mtr room) for MAJHIGRAM SINGOT water supply schemes under Katwa Sub-Division within Burdwan Division, PHE Dte. [ G.L to P.L Height= 1.20 Mtr] (Sl No-1) | Assistant Engineer |  | ORD/000273/2021-2022 | 798/KTS | 10/12/2021 | 08/02/2022 | BABUL SK | 3.24 | 2.91 | 89.77 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Construction of sanitary Latrine and water supply arrangement at Head Work Site of Majhigram Singot piped water supply schemes under Mongalkote Block under Katwa Sub-Division under Burdwan Division, PHE Dte.[Sl No-01] | Assistant Engineer |  | ORD/000593/2021-2022 | 159/KTS | 24/02/2022 | 17/03/2022 | BABUL SK | 1.76 | 1.72 | 97.44 | 1
5 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Supply , delivery & Installation of Submersible Pumping Machinery , Voltage stabiliser , Chlorinator and Internal House wiring for Tube well No. 3 of Majhigram Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. [ Block- Mongalkoat ] | ASSISTANT ENGINEER |  | ORD/000013/2022-2023 | 1173/CMD | 27/06/2022 | 27/07/2022 | MITRA ENTERPRISE | 9.22 | 9.03 | 97.86 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000163/2021-2022 | 1323/BWD | 08/03/2022 | 08/03/2022 | Resource Division | 16 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2021-2022 | 545/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 16.58 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000219/2021-2022 | 1553/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000181/2021-2022 | 1376/BWD | 09/03/2022 | 09/03/2022 | Resource Division | 3.83 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2022-2023 | 3275/BWD | 29/07/2022 | 29/07/2022 | Resource Division | 34.57 | 0 | 0 | 0
Total | [13 empty] | 3093.21 | 16.28 | 0.53