## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09715 | Augmentation | Route Survey & Preparation of DPR for BHATAKUL PWSS under Durgapur(Bardhaman North) Sub-Division under Burdwan Division PHE Dte.[SL-F] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000657/2021-2022 | 106/DSD | 18/02/2022 | 05/03/2022 | SIRCON ENGINEERING SERVICES | 2.63 | 2.63 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09715 | Augmentation | Supply of materials for different water supply schemes under Burdwan Division, PHE Dte. |  |  | VCH/001555/2021-2022 | 1194/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 62.76 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09715 | Augmentation | Shifting of 25 KVA S/STN with Selenda 11KV HTOH Line from the premises of Bhatakul PWSS under Burdwan Division, PHE Dte. |  |  | VCH/000653/2022-2023 | 550/DW/22-23 | 13/09/2022 | 13/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.43 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09715 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09715 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augmentation of Bhatakul (Zone-I) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER |  | ORD/000620/2022-2023 | 2093/CMD | 08/09/2022 | 08/10/2022 | CHOUDHURY ENTERPRISE | 10.82 | 10.73 | 99.15 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09715 | Augmentation | Construction of Drum Sheet Walling and Approach road to HW site for Augmentation of Bhatakul (Zone-I ) Piped water supply Scheme , P.H.E Dte. Block:-Bhatar, Dist: Purba Bardhaman. SL-13 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000534/2022-2023 | 653/DSD | 03/11/2022 | 03/12/2022 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 2.99 | 2.99 | 100 | 100
7 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09715 | Augmentation | Restoration of power line for New Well No. 1 at Bhatakul (Zone - I) Water Supply Scheme, under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER |  | ORD/000781/2022-2023 | 1370/CMSD - I | 30/12/2022 | 14/01/2023 | CHOUDHURY ENTERPRISE | 1.66 | 1.66 | 100 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09715 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2021-2022 | 548/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 9.39 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09715 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000220/2021-2022 | 1543/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09715 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000192/2021-2022 | 1374/BWD | 09/03/2022 | 09/03/2022 | Resource Division | 3.83 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09715 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000172/2021-2022 | 1338/BWD | 08/03/2022 | 08/03/2022 | Resource Division | 56.67 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09715 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000100/2021-2022 | 768/BWD | 07/02/2022 | 07/02/2022 | Resource Division | 38.41 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09715 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2022-2023 | 3276/BWD | 29/07/2022 | 29/07/2022 | Resource Division | 69.15 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09715 | Augmentation | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tubewell site for Augmentation of BHATAKUL (Zone-I & II) Piped Water Supply Scheme, Block - Bhatar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000014/2022-2023 | 1962/BWD | 12/04/2022 | 27/05/2022 | ACME CONSTRUCTION | 22.05 | 16.19 | 73.41 | 100
15 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09715 | Augmentation | Augmentation of BHATAKUL Piped Water Supply Scheme (Zone - I & II) including Laying Distribution System, Functional Household Tap Connection, Pumping Main, 350 Cum capacity Over Head Reservoir with 20 Mtr. staging height (including Soil Testing), Switch Room with sanitary arrangement, construction of Boundary wall in Head work site and repairing of pump house at Bhatar Block in under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000398/2021-2022 | 277/BWD | 14/01/2022 | 02/11/2023 | SATYANARAYAN ENGINEERS CO. OP. SOCIETY LTD. | 351.08 | 206.56 | 58.83 | 100
16 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09715 | Augmentation | Quotation from WBSEDCL for Augmentation of Bhatakul Zone-2 water supply scheme for P.H.-2 under Burdwan Division, PHE Dte. |  |  | BILL/00390/2024-2025 | 536/JJM | 18/07/2024 | 18/07/2024 | WBSEDCL | 11.79 | 0 | 0 | 0
17 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09715 | Augmentation | Quotation for new service connection for Bhatakul PWSS Zone-2, PH-2. |  |  | BILL/00309/2024-2025 |  | 19/06/2024 | 19/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 11.79 | 0 | 0 | 0
Total | [13 empty] | 3662.83 | 240.76 | 6.57