## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | Augmentation of SAJIARA Piped Water Supply Scheme with LDS, Rising Main, Switch Room (with & without water supply & sanitary arrangements), Construction 300 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test & Construction of Boundary wall under Kalna Sub-Division, Block - Purbasthali - II, Dist. - Purba Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000432/2021-2022 | 645/BWD | 01/02/2022 | 01/02/2023 | UNICON INDIA | 318.07 | 39.69 | 12.48 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tubewell site for SAJIARA Piped Water Supply Scheme, Block - Purbasthali - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000012/2022-2023 | 1960/BWD | 12/04/2022 | 27/05/2022 | ACME CONSTRUCTION | 14.81 | 13.62 | 91.93 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | Preparation of DPR for augmentation of Sajiara W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-D) | Assistant Engineer |  | ORD/000516/2021-2022 | 184/KSD | 21/02/2022 | 14/03/2022 | M/S R. DUTTA & CO. | 2.88 | 2.88 | 100 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2021-2022 | 546/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 15.25 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000147/2021-2022 | 1244/BWD | 07/03/2022 | 07/03/2022 | Resource Division | 2.64 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000171/2021-2022 | 1339/BWD | 08/03/2022 | 08/03/2022 | Resource Division | 53.75 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000241/2021-2022 | 1565/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2022-2023 | 3274/BWD | 29/07/2022 | 29/07/2022 | Resource Division | 34.57 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augumentation of Sajiara Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000064/2023-2024 | 2567/CMD | 06/06/2023 | 06/07/2023 | AMUSAR IMPEX PVT. LTD. | 21.95 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | Laying of Rising Main for Augmentation of SAJIARA Piped Water Supply Scheme to provide house connection within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000597/2023-2024 | 3766/BWD | 29/08/2023 | 28/09/2023 | CHOWDHURY CONSTRUCTION | 8.19 | 0 | 0 | 2
12 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | Work Order for "Construction of Pump house cum chlorine room without sanitary (Size 3.60 mtr x 3.00 mtr room) at 2nd Tube well site for augmentation of Sajiara Water Supply Scheme for providing Functional Household Tap Connection (FHTC) within Kalna Sub-Division under Burdwan Division, PHE Dte.^". |  | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000552/2023-2024 | 1307/KSD | 23/08/2023 | 22/10/2023 | BUILD-TECH | 3.02 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | Work Order for "Construction of Pump house cum chlorine room without sanitary (Size 3.60 mtr x 3.00 mtr room) at 2nd Tube well site for augmentation of Sajiara Water Supply Scheme for providing Functional Household Tap Connection (FHTC) within Kalna Sub-Division under Burdwan Division, PHE Dte.^". | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000559/2023-2024 | 1307/KSD | 23/08/2023 | 22/10/2023 | BUILD-TECH | 3.02 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | Construction of Pump House cum chlorine room with sanitary and water supply arrangement at Head Work Site for augmentation of SAJIARA according to departmental drawing No-PHE/BD/P.H/DRG-01/DEC-2017 (Size 3.30 mtr x 3.60 mtr room with 1.2 Mtr. wide verandah) to provide house connection within Kalna Sub-Division under Burdwan Division, PHE Dte._2ND CALL | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000964/2023-2024 | 5713/BWD | 29/12/2023 | 27/02/2024 | DEL DELTA CONSTRUCTION | 5.2 | 0 | 0 | 0
15 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | Construction of boundary wall of SAJIARA Piped water supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Length -150 Mtr, No of Columns-43 Nos. Centre to Centre- 3.5 Mtr.) With Double Tie Beam. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000598/2023-2024 | 4172/BWD | 21/09/2023 | 21/10/2023 | HAIDER ALI MONDAL | 14.53 | 3.84 | 26.4 | 80
16 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | Laying distribution system for augmentation of SAJIARA W/S Scheme to provide house connection within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000512/2023-2024 | 3554/BWD | 11/08/2023 | 25/09/2023 | SK RAJU | 42.39 | 32.46 | 76.59 | 40
17 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | Different types of works involve in connection with Augmentation of SAJIARA (SM/09716), NAMA BHANDARTIKURI (SM/14917) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000394/2024-2025 | 3010/BWD | 02/08/2024 | 30/03/2025 | PRATIMA CONSTRUCTION | 79.16 | 0 | 0 | 2
18 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | Quotation from WBSEDCL for Load Enhancement charges of Sajiara water supply scheme of PH-1. under Burdwan Division, PHE Dte. |  |  | BILL/01725/2023-2024 | 1402/JJM | 29/02/2024 | 29/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.32 | 0 | 0 | 0
19 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | WBSEDCL Quotation for new service connection Sajiara TW. NO.-05 |  |  | BILL/01637/2024-2025 |  | 06/03/2025 | 06/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.79 | 0 | 0 | 0
20 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | SM/09716 | Augmentation | WBSEDCL Quotation for new service connection Sajiara TW. NO.-04 |  |  | BILL/01636/2024-2025 |  | 06/03/2025 | 06/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.69 | 0 | 0 | 0
Total | [13 empty] | 3634.6 | 92.49 | 2.54