## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09717 | Augmentation | Preparation of DPR for augmentation of Kaigram W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No- E) | Assistant Engineer |  | ORD/000517/2021-2022 | 185/KSD | 21/02/2022 | 14/03/2022 | LEMNISCATE | 2.66 | 2.66 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09717 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09717 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000079/2021-2022 | 605/BWD | 28/01/2022 | 28/01/2022 | Resource Division | 24.12 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09717 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2021-2022 | 533/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 16.17 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09717 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000106/2021-2022 | 905/BWD | 15/02/2022 | 15/02/2022 | Resource Division | 12.41 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09717 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000239/2021-2022 | 1563/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09717 | Augmentation | Augmentation of KAIGRAM Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction 250 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test & Construction of Boundary wall under Kalna Sub-Division, Block - Monteswar, Dist. - Purba Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000436/2021-2022 | 697/BWD | 02/02/2022 | 02/02/2023 | B.B.C. ENTERPRISE | 291.4 | 234.3 | 80.41 | 80
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09717 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tubewell site for KAIGRAM Piped Water Supply Scheme, Block - Monteswar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000011/2022-2023 | 1959/BWD | 12/04/2022 | 27/05/2022 | ACME CONSTRUCTION | 14.81 | 13.92 | 94 | 100
9 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09717 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augumentation of Kaigram Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2023-2024 | 2564/CMD | 06/06/2023 | 06/07/2023 | CHOUDHURY ENTERPRISE | 20.45 | 19.89 | 97.29 | 98
10 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09717 | Augmentation | Work Order for "Constrcution of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around Other than head work site for Augmentation of Kaigram Piped Water Supply Scheme (SM/09717) within Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001186/2023-2024 | 2190/KSD | 15/03/2024 | 25/03/2024 | PARTHA PRATIM ACHARYA | 4.56 | 4.56 | 100 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09717 | Augmentation | Work Order for " Renovation of Pump House for Augmentation of Kaigram Piped Water Supply Scheme (SM/09717) under Kalna Sub-Division under Burdwan Division, PHE Dte. (1 no Pump House Repairing)" | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001193/2023-2024 | 2203/KSD | 18/03/2024 | 28/03/2024 | PARTHA PRATIM ACHARYA | 1.28 | 1.27 | 99.32 | 100
12 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09717 | Augmentation | Quotation for new service connection (Load enhancement) at Kaigram PWSS PH-2. |  |  | BILL/00461/2024-2025 |  | 30/07/2024 | 30/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.48 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09717 | Augmentation | Quotation from WBSEDCL for load enhancement of Kaigram water supply scheme for P.H.-1 & 2 under Burdwan Division, PHE Dte. |  |  | BILL/00549/2024-2025 | 732/JJM | 27/08/2024 | 27/08/2024 | WBSEDCL | 5.01 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09717 | Augmentation | Quotation for new service connection (Load enhancement) at Kaigram PWSS PH-1. |  |  | BILL/00462/2024-2025 |  | 30/07/2024 | 30/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.53 | 0 | 0 | 0
15 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09717 | Augmentation | Providing of balance FHTC and other allied works at Kaigram Mouza under the command area of Kaigram Piped Water Supply Scheme (SM/09717) in order to declare Sajalgram under Mamudpur GP-II under Manteshwar Block under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000020/2025-2026 | 1247/BWD | 23/04/2025 | 23/05/2025 | MONDAL & CO. | 18.95 | 0 | 0 | 80
16 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09717 | Augmentation | Providing of balance FHTC and other allied works at Rautgram Mouza under the command area of Kaigram Piped Water Supply Scheme (SM/09717) in order to declare Sajalgram under Mamudpur GP-II under Manteshwar Block under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000022/2025-2026 | 1249/BWD | 23/04/2025 | 23/05/2025 | MONDAL & CO. | 28.94 | 0 | 0 | 50
Total | [13 empty] | 3451.13 | 276.61 | 8.01