## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. | SM/09718 | Augmentation | Preparation of DPR for augmentation of Patuli W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-A) | Assistant Engineer |  | ORD/000513/2021-2022 | 181/KSD | 21/02/2022 | 14/03/2022 | M/S R. DUTTA & CO. | 3.75 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. | SM/09718 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. | SM/09718 | Augmentation | Supply of materials for different water supply schemes under Burdwan Division, PHE Dte. |  |  | VCH/001555/2021-2022 | 1194/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 62.76 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. | SM/09718 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augumentation of Patuli (Zone - II) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000065/2023-2024 | 2566/CMD | 06/06/2023 | 06/07/2023 | M/S. S.R. ENTERPRISE | 21.77 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. | SM/09718 | Augmentation | Work Order for "Replacement of Valve and Restoration of Concrete Roads at Patuli Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." |  | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000549/2023-2024 | 1304/KSD | 23/08/2023 | 22/09/2023 | IYASIN DAFADAR | 4.09 | 0 | 0 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. | SM/09718 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2021-2022 | 7348/BWD | 30/12/2021 | 30/12/2021 | Resource Division | 13.73 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. | SM/09718 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000183/2021-2022 | 1378/BWD | 09/03/2022 | 09/03/2022 | Resource Division | 4.45 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. | SM/09718 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000165/2021-2022 | 1325/BWD | 08/03/2022 | 08/03/2022 | Resource Division | 74.18 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. | SM/09718 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2021-2022 | 557/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 22.05 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. | SM/09718 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000233/2021-2022 | 1557/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. | SM/09718 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000097/2021-2022 | 769/BWD | 07/02/2022 | 07/02/2022 | Resource Division | 51.93 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. | SM/09718 | Augmentation | Load enhancement charges of Aug of Patuli water supply scheme under Burdwan Division, PHE Dte. |  |  | BILL/00563/2023-2024 | 665/JJM | 21/09/2023 | 21/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.03 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. | SM/09718 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at H.W & 2nd Tubewell site for PATULI (Zone-I & II) Piped Water Supply Scheme, Block - Purbasthali - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 + 2 = 4 Nos. GTW]. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000640/2021-2022 | 1621/BWD | 21/03/2022 | 09/01/2025 | AUXILIARY TUBE WELL DRILLERS | 31.66 | 0 | 0 | 50
14 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. | SM/09718 | Augmentation | Augmentation of PATULI Water Supply Scheme (Zone-I & II) with LDS, Rising Main, FHTC work, Pump House & Boundary Wall of Purbasthali - II Block in Kalna Sub-Division, District - Purba Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000384/2021-2022 | 256/BWD | 13/01/2022 | 12/07/2022 | IJABUL SEKH | 407.57 | 0 | 0 | 80
15 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. | SM/09718 | Augmentation | Work Order for " Restoration of Pipeline and Other Allied Works i.c.w. Augmentation of PATULI(SM/09718) Piped Water Supply Scheme under PURBASTHALI-II Block,Kalna Sub-Division, District:- Purba Bardhaman." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001187/2023-2024 | 2191/KSD | 15/03/2024 | 25/03/2024 | IYASIN DAFADAR | 4.52 | 0 | 0 | 2
16 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. | SM/09718 | Augmentation | Quotation from WBSEDCL for new service connection of Augmentation of Patuli TW-3 Water supply scheme under Burdwan Division, PHE Dte. |  |  | BILL/00666/2024-2025 | 826/JJM | 18/09/2024 | 18/09/2024 | WBSEDCL | 7.53 | 0 | 0 | 0
17 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. | SM/09718 | Augmentation | Different types of works involve in connection with Augmentation of JHAUDANGA (SM/16293), KASHIPUR (SM/16297), PATULI (SM/09718) & PARULIA (SM/09719) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000163/2024-2025 | 2202/BWD | 13/06/2024 | 06/03/2026 | MONDAL PRECISION PVT LTD | 570 | 0 | 0 | 2
Total | [13 empty] | 4294.02 | 0 | 0