## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09719 | Augmentation | Preparation of DPR for augmentation of Parulia W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-D) | Assistant Engineer |  | ORD/000582/2021-2022 | 216/KSD | 24/02/2022 | 17/03/2022 | M/S R. DUTTA & CO. | 2.84 | 2.79 | 98.37 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09719 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09719 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for 2nd TW Site of Aug. of PARULIA & its adjoining mouzas Piped Water Supply Scheme, Block ? Purbasthali ? II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000549/2022-2023 | 5126/BWD | 21/11/2022 | 21/12/2022 | M/S SYCHROTECH INDUSTRY | 8.72 | 8.18 | 93.81 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09719 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000034/2021-2022 | 535/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 14.55 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09719 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000080/2021-2022 | 604/BWD | 28/01/2022 | 28/01/2022 | Resource Division | 24.12 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09719 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000108/2021-2022 | 906/BWD | 15/02/2022 | 15/02/2022 | Resource Division | 6.93 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09719 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000240/2021-2022 | 1564/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09719 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2022-2023 | 4632/BWD | 17/10/2022 | 17/10/2022 | Resource Division | 12.32 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09719 | Augmentation | Augmentation of PARULIA Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction 300 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test & Construction of Boundary wall under Kalna Sub-Division, Block ¿ Purbasthali ¿ II, Dist. - Purba Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000437/2021-2022 | 699/BWD | 02/02/2022 | 02/02/2023 | M/S ASHA CONSTRUCTION | 407.54 | 379.29 | 93.07 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) | SM/09719 | Augmentation | Different types of works involve in connection with Augmentation of JHAUDANGA (SM/16293), KASHIPUR (SM/16297), PATULI (SM/09718) & PARULIA (SM/09719) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000163/2024-2025 | 2202/BWD | 13/06/2024 | 06/03/2026 | MONDAL PRECISION PVT LTD | 570 | 0 | 0 | 2
Total | [13 empty] | 4052.37 | 390.26 | 9.63