## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09873 | Augmentation | Preparation of DPR for augmentation of Radhanagar-Baghnapara W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | Assistant Engineer |  | ORD/000579/2021-2022 | 214/KSD | 24/02/2022 | 17/03/2022 | ROY CHOUDHURI CONSTRUCTION | 2.96 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09873 | Augmentation | Preparation of DPR for augmentation of Radhanagar-Baghnapara W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | Assistant Engineer |  | ORD/000580/2021-2022 | 214/KSD | 24/02/2022 | 17/03/2022 | ROY CHOWDHURY ASSOCIATES | 2.96 | 2.95 | 99.59 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09873 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09873 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2021-2022 | 537/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 17.54 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09873 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000221/2021-2022 | 1544/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09873 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000193/2021-2022 | 1375/BWD | 09/03/2022 | 09/03/2022 | Resource Division | 4.85 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09873 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 3277/BWD | 29/07/2022 | 29/07/2022 | Resource Division | 65.16 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09873 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 3 at Augumentation of Radhanagar Baghnapara Water Supply Scheme [ BLOCK- Kalna-I ]under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001643/2023-2024 | 1625/CMD | 15/03/2024 | 14/04/2024 | JOYGURU ENTERPRISE | 12.31 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09873 | Augmentation | Augmentation of Radhanagar Baghnapara Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 200 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation & repairing of existing 180 cum OHR with repairing of switch rooms, boundary walls at different TW site under Kalna-I Block, District:- Purba-Burdwan | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000476/2023-2024 | 3511/BWD | 10/08/2023 | 30/03/2025 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 458.55 | 165.42 | 36.08 | 70
10 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/09873 | Augmentation | Sinking of additional Tube Well, construction of pump house & boundary wall & laying interconnection of RADHANAGAR BAGHNAPARA Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (PP Site- Khaspur Karim Gachhi). | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000882/2023-2024 | 5483/BWD | 13/12/2023 | 01/02/2025 | MUKHERJEE ENTERPRISE | 26.91 | 14.32 | 53.21 | 45
Total | [13 empty] | 3596.6 | 182.69 | 5.08