## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | SM/09921 | Augmentation | Preparation of DPR for augmentation of Satgachhi W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | Assistant Engineer |  | ORD/000514/2021-2022 | 182/KSD | 21/02/2022 | 14/03/2022 | M/S R. DUTTA & CO. | 3.27 | 3.22 | 98.62 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | SM/09921 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | SM/09921 | Augmentation | Extension of 75 mm dia pipeline at Miya Para, Modhya Bohar & Bhagar Para Purba Bohar regarding FHTC under Satgachia (Zone-I) water supply scheme under Burdwan Division, PHE Dte.[Gr.-A] | Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000350/2021-2022 | 703/BSD | 11/06/2021 | 16/06/2021 | M/S SAYAN CHAKRABORTY | 0.88 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | SM/09921 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000173/2021-2022 | 1331/BWD | 08/03/2022 | 08/03/2022 | Resource Division | 160.86 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | SM/09921 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2021-2022 | 551/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 39.34 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | SM/09921 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000222/2021-2022 | 1545/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | SM/09921 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000194/2021-2022 | 1388/BWD | 09/03/2022 | 09/03/2022 | Resource Division | 4.6 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | SM/09921 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2022-2023 | 3273/BWD | 29/07/2022 | 29/07/2022 | Resource Division | 33.26 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | SM/09921 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 4630/BWD | 17/10/2022 | 17/10/2022 | Resource Division | 12.32 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | SM/09921 | Augmentation | New service connection charges for Aug. of Satgachi PWSS TW-4 |  |  | BILL/01395/2023-2024 | BP-2023-24-137 | 25/08/2023 | 25/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.67 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | SM/09921 | Augmentation | New service connection charges for Aug. of Satgachi PWSS TW-3 |  |  | BILL/01393/2023-2024 | BP-2023-24-136 | 25/08/2023 | 25/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.05 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | SM/09921 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augumentation of Satgachi Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. [2nd CALL] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000210/2023-2024 | 3046/CMD | 20/07/2023 | 19/08/2023 | AMUSAR IMPEX PVT. LTD. | 21.98 | 21.21 | 96.52 | 95
13 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | SM/09921 | Augmentation | Sinking of additional 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SATGACHHI Piped Water Supply Scheme, Block - Kalna - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000069/2022-2023 | 2423/BWD | 11/05/2022 | 10/06/2022 | M/S SYCHROTECH INDUSTRY | 9.01 | 8.56 | 95.05 | 100
14 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | SM/09921 | Augmentation | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 03 Nos. Piped W/S. Schemes under Kalna II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000336/2024-2025 | 3016/BWD | 05/08/2024 | 25/08/2024 | HORIZEN | 7.55 | 2.5 | 33.1 | 100
15 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | SM/09921 | Augmentation | Quotation for new service connection at Satgachi PWSS PH 5 |  |  | BILL/00933/2024-2025 | BP-2024-25-351 | 05/10/2024 | 05/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.59 | 0 | 0 | 0
16 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | SM/09921 | Augmentation | Augmentation of SATGACHI Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 700 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation including construction of switch-room (3.60mx3.0m) & boundary wall under Kalna-II Block, District:- Purba-Burdwan. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000065/2022-2023 | 2339/BWD | 10/05/2022 | 31/03/2025 | P.B. ENTERPRISE | 727.47 | 593.81 | 81.63 | 100
17 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | SM/09921 | Augmentation | Supply of various D.I. Mechanical joints & specials for Aug. of SATGACHI & Aug. of BAIDYAPUR Piped W/S. Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. [Part-B]. | AE(HQs) | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000304/2024-2025 | 2827/BWD | 19/07/2024 | 20/02/2025 | KEJRIWAL CASTINGS LIMITED | 4.82 | 0 | 0 | 100
18 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | SM/09921 | Augmentation | Supply of various D.I. Mechanical joints & specials for Aug. of SATGACHI & Aug. of BAIDYAPUR Piped W/S. Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. [Part-A]. | AE(HQs) | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000315/2024-2025 | 2839/BWD | 19/07/2024 | 19/02/2025 | ELECTROSTEEL CASTING LIMITED | 4.95 | 0 | 0 | 100
19 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | SM/09921 | Augmentation | Supply of various D.I. Mechanical joints & specials for Aug. of SATGACHI & Aug. of BAIDYAPUR Piped W/S. Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. [Part-C]. | AE(HQs) | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000308/2024-2025 | 2831/BWD | 19/07/2024 | 01/03/2025 | JINDAL SAW LTD. | 4.63 | 0 | 0 | 100
Total | [13 empty] | 4053.63 | 629.31 | 15.52