## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | Preparation of DPR for augmentation of Baidyapur W/S Scheme (Zone-I & II) within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-A) | Assistant Engineer |  | ORD/000568/2021-2022 | 203/KSD | 23/02/2022 | 16/03/2022 | INDRANIL DUTTA & ASSOCIATES | 4.19 | 4.17 | 99.6 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for 2nd TW Site of Aug. of BAIDYAPUR (Z-II) & its adjoining mouzas Piped Water Supply Scheme, Block ? Kalna ? II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte._2ND CALL. | Assistant Engineer |  | ORD/000567/2022-2023 | 5274/BWD | 30/11/2022 | 30/12/2022 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 7.33 | 6.97 | 95.04 | 0
3 | PURBA BARDHAMAN |  | Central Mechanical | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Augmentation of BAIDYAPUR PWSS under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000912/2022-2023 | 1036/CMD | 02/03/2023 | 01/04/2023 | BEHERA ENTERPRISE | 11.46 | 11.13 | 97.18 | 80
4 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Aug. of BAIDYAPUR (Z-I) PWSS, Block - Kalna - II and NANDAI PWSS, Block - Kalna - I Piped Water Supply Scheme, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 02 Nos. Tube well]. |  |  | ORD/000151/2023-2024 | 2424/BWD | 30/05/2023 | 14/07/2023 | KOUSIK MALLICK | 19.84 | 9.14 | 46.09 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2022-2023 | 3272/BWD | 29/07/2022 | 29/07/2022 | Resource Division | 31.47 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | New service connection quotation from WBSEDCL of Augmentation of Baidyapur Z-II (T.W.-3) under Burdwan Division, PHE Dte. |  |  | BILL/00098/2023-2024 | 194/JJM | 31/05/2023 | 31/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.56 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | Work Order for "Restoration in pipe connection of Augmentation scheme of Baidyapur Zone-II Piped Water Supply Scheme under Kalna Sub-Division under Burdwan Division, PHE Dte." (SL-3) | Assistant Engineer | JUNIOR ENGINEER RWS KALNA2 | ORD/001133/2023-2024 | 2062/KSD | 23/02/2024 | 14/03/2024 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 1.37 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | Construction of switch rooms & Rising main at different TW site for Baidyapur (Zone-I) Piped Water Supply Scheme under Kalna - II Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER RWS KALNA2 | ORD/000529/2023-2024 | 3626/BWD | 21/08/2023 | 20/10/2023 | M/S UNIQUE | 9.11 | 6.67 | 73.21 | 65
9 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | Work Order for "Renovation of Pump House for Augmentation 1 of Baidyapur (Zone-II) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER RWS KALNA2 | ORD/001241/2023-2024 | 1953/KSD | 05/02/2024 | 01/03/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.59 | 0.54 | 91.73 | 100
10 | PURBA BARDHAMAN |  | Central Mechanical | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | Supply & Installation of Chlorination System for Tube well No.-1 at Baidyapur (zone-1) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001863/2023-2024 | 461/CMSD | 21/03/2024 | 02/04/2024 | SUDIKSHA CONSTRUCTION | 0.96 | 0.96 | 100 | 100
11 | PURBA BARDHAMAN |  | Central Mechanical | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | Supply and delivery of different Electro-mechanical items for Baidyapur zone-1 Water Supply Scheme PH 1 replacement T.W (part-1) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001670/2023-2024 | 64/CMSD | 11/01/2024 | 23/01/2024 | SUBRATA BHADRA | 0.96 | 0.94 | 98.25 | 100
12 | PURBA BARDHAMAN |  | Central Mechanical | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | House wiring, double earthing and allied works for Baidyapur zone-1 Water Supply Scheme PH 1 replacement T.W (part-2) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001674/2023-2024 | 80/CMSD | 15/01/2024 | 27/01/2024 | SUBRATA BHADRA | 0.97 | 0.97 | 100 | 100
13 | PURBA BARDHAMAN |  | Central Mechanical | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | Quotation for new service connection at Baidyapur Zone-2 PWSS PH-3 |  |  | BILL/00390/2024-2025 | BP-2024-25-200 | 18/07/2024 | 18/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.14 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Central Mechanical | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | Quotation for load enhancement at Baidyapur PH2 |  |  | BILL/00810/2024-2025 | BP-2024-25-302 | 24/09/2024 | 24/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.35 | 0 | 0 | 0
15 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | Augmentation of Baidyapur (Zone-I & II) Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 200 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation including repairing of OHR, boundary walls & switch rooms under Kalna-II Block, District:- Purba-Burdwan. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000116/2022-2023 | 2859/BWD | 22/06/2022 | 02/11/2025 | SUPRITI ENTERPRISE | 734.07 | 712.21 | 97.02 | 60
16 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | Additional pipe laying of HDPE pipeline & providing FHTC work at Sanpukur, Mirhat village under BAIDYAPUR Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER RWS KALNA2 | ORD/000871/2023-2024 | 5308/BWD | 01/12/2023 | 15/05/2024 | GENUINE ENGINEERING CO-OP. SOCIETY LTD. | 35.01 | 26.03 | 74.37 | 1
17 | PURBA BARDHAMAN |  | Central Mechanical | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 5 & 6 at Augumentation of BAIDYAPUR Water Supply Scheme [BLOCK- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001618/2023-2024 | 1542/CMD | 05/03/2024 | 04/05/2025 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 24.62 | 0 | 0 | 50
18 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001144/2024-2025 | 618/BWD | 11/02/2025 | 10/08/2025 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0 | 0
19 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | Supply of various D.I. Mechanical joints & specials for Aug. of SATGACHI & Aug. of BAIDYAPUR Piped W/S. Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. [Part-B]. | AE(HQs) | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000304/2024-2025 | 2827/BWD | 19/07/2024 | 20/02/2025 | KEJRIWAL CASTINGS LIMITED | 4.82 | 0 | 0 | 100
20 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | Supply of various D.I. Mechanical joints & specials for Aug. of SATGACHI & Aug. of BAIDYAPUR Piped W/S. Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. [Part-A]. | AE(HQs) | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000315/2024-2025 | 2839/BWD | 19/07/2024 | 19/02/2025 | ELECTROSTEEL CASTING LIMITED | 4.95 | 0 | 0 | 100
21 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | SM/10032 | Augmentation | Supply of various D.I. Mechanical joints & specials for Aug. of SATGACHI & Aug. of BAIDYAPUR Piped W/S. Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. [Part-C]. | AE(HQs) | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000308/2024-2025 | 2831/BWD | 19/07/2024 | 01/03/2025 | JINDAL SAW LTD. | 4.63 | 0 | 0 | 100
Total | [13 empty] | 1488.5 | 779.75 | 52.38