## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10056 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10056 | Augmentation | Route Survey & Preparation of DPR for Sasinara (Zone-II) & (Zone-III) W/S Scheme under Burdwan-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.2. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000491/2021-2022 | 177/BSD | 31/01/2022 | 02/03/2022 | RADIANT | 3.76 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10056 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SASINARA Z-II W/S Scheme at Kalsi Mouza, RASULPUR W/S Scheme at 4th TW site & ALIPUR W/S Scheme at 4th TW site under Memari-I Block under within Burdwan Sub-Division, PHE Dte. [For 3 Nos. Tube well]. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000159/2023-2024 | 2455/BWD | 31/05/2023 | 30/07/2023 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 39.76 | 0 | 0 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10056 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000175/2021-2022 | 1332/BWD | 08/03/2022 | 08/03/2022 | Resource Division | 108.97 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10056 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000223/2021-2022 | 1546/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10056 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000195/2021-2022 | 1387/BWD | 09/03/2022 | 09/03/2022 | Resource Division | 4.83 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10056 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2022-2023 | 4851/BWD | 20/10/2022 | 20/10/2022 | Resource Division | 10.47 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10056 | Augmentation | Quotation for WBSEDCL for New Service connection of Sasinara Z-II TW-3 water supply scheme. |  |  | BILL/01244/2023-2024 | 1149/JJM | 29/12/2023 | 29/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.03 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10056 | Augmentation | Providing Balance Functional Household Tap Connection (850nos FHTC) from existing distribution system within the command area of SASINARA ZONE-II Piped Water Supply Scheme at (Sasinara, Kalsi, Debipur, Amadpur, Maheshpur, Mobarakpur) Mouza, Construction of boundary wall at head work site, 2nd T/W & 3rd T/W site under MEMARI-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000531/2023-2024 | 3628/BWD | 21/08/2023 | 20/10/2023 | A R TRADERS | 69.4 | 0 | 0 | 99
10 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10056 | Augmentation | Construction of switch rooms & Rising main at different TW site for SASINARA (Zone-II) Piped Water Supply Scheme under Memari - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000654/2023-2024 | 4165/BWD | 20/09/2023 | 19/11/2023 | PAL CONSTRUCTION | 9.12 | 0 | 0 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10056 | Augmentation | Augmentation of SASINARA ZONE-II Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 350 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under MEMARI- I Block, District:- Purba-Burdwan. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000123/2022-2023 | 2929/BWD | 28/06/2022 | 29/11/2024 | ASHOK KUMAR GHOSH | 481.08 | 0 | 0 | 100
Total | [13 empty] | 3738.8 | 0 | 0