## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10057 | Augmentation | Route Survey & Preparation of DPR for Sasinara (Zone-I) W/S Scheme under Memari-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.3 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000511/2021-2022 | 178/BSD | 31/01/2022 | 02/03/2022 | APEX ENGINEERING | 3.01 | 3 | 99.76 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10057 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10057 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000154/2021-2022 | 1246/BWD | 07/03/2022 | 07/03/2022 | Resource Division | 4.36 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10057 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000226/2021-2022 | 1554/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10057 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000174/2021-2022 | 1333/BWD | 08/03/2022 | 08/03/2022 | Resource Division | 51.36 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10057 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 4853/BWD | 20/10/2022 | 20/10/2022 | Resource Division | 13.55 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10057 | Augmentation | Restoration of Pump House at Head Work site of SASINARA ZONE-I Piped water supply scheme at Memari-I Block under Burdwan Division, Dist.-Purba Bardhaman. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000182/2024-2025 | 1004/BSD | 06/06/2024 | 06/07/2024 | MS MOLLA CONSTRUCTION | 0.96 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10057 | Augmentation | Quotation for new service connection at Sasinara W/S (Aug) Z-1, TW-3. |  |  | BILL/00931/2024-2025 | BP-2024-25-350 | 05/10/2024 | 05/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.88 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10057 | Augmentation | Construction of switch rooms & Rising main at different TW site for SASINARA (Zone-I) Piped Water Supply Scheme under Memari - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000577/2023-2024 | 3725/BWD | 25/08/2023 | 01/05/2025 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 9.03 | 0 | 0 | 90
10 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10057 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Zone- 1 & 2, Tube well No.-3 at Augumentation of SASINARA Water Supply Scheme [BLOCK- MEMARI-I] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000035/2024-2025 | 2138/CMD | 05/07/2024 | 03/09/2024 | C.M. ENTERPRISE | 24.63 | 11.53 | 46.82 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10057 | Augmentation | Designing,making and erection of Sign Board for SWAJAL GRAM in Dharmma Simla village of Memari-I Block under Sasinara(Zone-I) Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte (5 Nos. Board) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000443/2025-2026 | 2307/BSD | 19/08/2025 | 29/08/2025 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10057 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Chaupira village of Memari-I Block under Sasinara (Zone-I) Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. (5 nos Board) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000495/2025-2026 | 2364/BSD | 21/08/2025 | 31/08/2025 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10057 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Jot Chaitanya village of Memari-I Block under Sasinara(Z-I) Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte (5 nos Board) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000616/2025-2026 | 2368/BSD | 21/08/2025 | 31/08/2025 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10057 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SASINARA Z-I W/S Scheme at DEBIPUR Mouza under Memari-I Block and SATGACHIA Z-I W/S Scheme at BEGUNIA Mouza under Memari-II Block within Burdwan Sub-Division, PHE Dte. [For 02 Nos. Tube well]. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000192/2023-2024 | 2687/BWD | 08/06/2023 | 07/08/2023 | ANIRUDDHA FARUQUE | 26.48 | 12.12 | 45.76 | 50
15 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10057 | Augmentation | Replacement of Tube-well & Rising main at HEAD TW SITE for Aug. of BAGILA, SASINARA ZONE-I, SASINARA ZONE-II, Piped Water Supply Scheme within MEMARI-I Block under Burdwan Division, PHE. Dte. District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000974/2023-2024 | 027/BWD | 03/01/2024 | 03/03/2024 | KOUSIK MALLICK | 38.87 | 0 | 0 | 90
16 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10057 | Augmentation | Construction of boundary wall at 1st Tube well site for SASINARA ZONE- III PWSS under MEMARI - I Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000709/2024-2025 | 3706/BWD | 28/10/2024 | 26/01/2025 | S.M. ENTERPRISE | 10.59 | 0 | 0 | 100
17 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10057 | Augmentation | Providing Balance Functional Household Tap Connection (1057 Nos FHTC) from existing distribution system within the command area of SASINARA ZONE-I Piped Water Supply Scheme at (Chhotodhama, Debipur, Dharmasimla, Purnagram, Jotchaitanya, Chaupira, Gouripur, Poltara) Mouza, Construction of boundary wall at head work site, 2nd T/W & 3rd T/W site under MEMARI-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000158/2024-2025 | 2176/BWD | 12/06/2024 | 01/03/2025 | AMIT KUMAR ROY | 71.85 | 15.17 | 21.12 | 30
18 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10057 | Augmentation | Augmentation of SASINARA ZONE-I Piped Water Supply Scheme with LDS, FHTC, Rising main & Construction of 400 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under Memari-I Block, District:- Purba-Burdwan. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000127/2022-2023 | 2971/BWD | 30/06/2022 | 01/04/2026 | MRITYUNJOY MUKHERJEE & CO. | 658.71 | 491.42 | 74.6 | 70
19 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10057 | Augmentation | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | AE(HQs),Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 01/04/2026 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 0 | 85
Total | [13 empty] | 4238.42 | 533.24 | 12.58