## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED KUSUMGRAM (ZONE I AND ZONE II) PWSS TO ACCOMMODATE FHTC IN MANTESWAR BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10058 | Augmentation | Preparation of DPR for augmentation of Kusumgram W/S Scheme (Zone-I & II) within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | Assistant Engineer |  | ORD/000569/2021-2022 | 204/KSD | 23/02/2022 | 16/03/2022 | ROY CHOWDHURY ASSOCIATES | 3.93 | 3.91 | 99.53 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED KUSUMGRAM (ZONE I AND ZONE II) PWSS TO ACCOMMODATE FHTC IN MANTESWAR BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10058 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000056/2022-2023 | 5521/BWD | 23/12/2022 | 23/12/2022 | Resource Division | 32.81 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED KUSUMGRAM (ZONE I AND ZONE II) PWSS TO ACCOMMODATE FHTC IN MANTESWAR BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10058 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED KUSUMGRAM (ZONE I AND ZONE II) PWSS TO ACCOMMODATE FHTC IN MANTESWAR BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10058 | Augmentation | Supply , delivery & Installation of Submersible Pumping Machinery , Voltage stabiliser , Chlorinator and Internal House wiring for Tube well No. 3 of Kulut [ Kusumgram ] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER |  | ORD/000010/2022-2023 | 1172/CMD | 27/06/2022 | 27/07/2022 | M/S. DAS ELECTRIC CO. | 9.33 | 8.93 | 95.77 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED KUSUMGRAM (ZONE I AND ZONE II) PWSS TO ACCOMMODATE FHTC IN MANTESWAR BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10058 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for 1ST TW Site of Aug. of KUSUMGRAM (Z-II) & its adjoining mouzas Piped Water Supply Scheme, Block ? Monteswar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. _2ND CALL. | Assistant Engineer |  | ORD/000657/2022-2023 | 371/BWD | 31/01/2023 | 02/03/2023 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 7.33 | 6.84 | 93.3 | 1
6 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED KUSUMGRAM (ZONE I AND ZONE II) PWSS TO ACCOMMODATE FHTC IN MANTESWAR BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10058 | Augmentation | Installation of Electro-mechanical accessories at Kusungram zone-1 PH-2 (replacement T.W) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000994/2023-2024 | 4361/CMD | 21/09/2023 | 21/10/2023 | BENGAL ELECTRICAL CONSTRUCTION | 1.97 | 1.97 | 100 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED KUSUMGRAM (ZONE I AND ZONE II) PWSS TO ACCOMMODATE FHTC IN MANTESWAR BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10058 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000224/2021-2022 | 1547/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED KUSUMGRAM (ZONE I AND ZONE II) PWSS TO ACCOMMODATE FHTC IN MANTESWAR BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10058 | Augmentation | Augmentation of Kusumgram Zone-I & II Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 450 & 300 cum capacity OHR with 20.0 mtr. Staging height including construction of switch-room without sanitary & water supply arrangement, boundary wall including repairing of boundary wall under Monteswar Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000541/2022-2023 | 5079/BWD | 17/11/2022 | 01/04/2025 | MANASH GHOSH | 778.07 | 693.66 | 89.15 | 66
Total | [13 empty] | 3838.81 | 715.31 | 18.63