## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE III PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10059 | Augmentation | Laying distribution and rising main pipeline including Providing Functional Household Tap Connection (FHTC) for augmentation of SASINARA ZONE III Piped Water Supply Scheme under MEMARI I Block, District: Purba Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000001/2022-2023 | 1839/BWD | 04/04/2022 | 04/05/2022 | THREE MAA ENTERPRISE | 49.71 | 49.6 | 99.78 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE III PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10059 | Augmentation | Laying of 90mm dia pipeline for SASINARA ZONE-III Piped Water Supply Scheme from Pump house to Nishraghar dharmatala via Annapurnatala under MEMARI- I Block under Burdwan Sub-Division under Burdwan Division, PHE Dte. Group.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000099/2022-2023 | 965/BSD | 14/06/2022 | 14/07/2022 | THREE MAA ENTERPRISE | 4.78 | 4.78 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE III PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10059 | Augmentation | Providing Balance Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SASINARA ZONE-III Piped Water Supply Scheme and under NISHRAGHAR Mouza under MEMARI-I Block of Burdwan Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000764/2022-2023 | 510/BSD | 21/03/2023 | 05/05/2023 | A R TRADERS | 3.51 | 3.49 | 99.63 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE III PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10059 | Augmentation | Route Survey & Preparation of DPR for Sasinara (Zone-II) & (Zone-III) W/S Scheme under Burdwan-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.2. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000491/2021-2022 | 177/BSD | 31/01/2022 | 02/03/2022 | RADIANT | 3.76 | 1.88 | 49.9 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE III PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10059 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000151/2021-2022 | 1245/BWD | 07/03/2022 | 07/03/2022 | Resource Division | 3.92 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE III PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10059 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000180/2021-2022 | 1337/BWD | 08/03/2022 | 08/03/2022 | Resource Division | 2.81 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE III PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10059 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000225/2021-2022 | 1548/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 1.32 | 0 | 0 | 0
Total | [13 empty] | 69.81 | 59.75 | 85.59