## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10060 | Augmentation | Route Survey & Preparation of DPR for Satgachia (Zone-I) & (Zone-II) W/S Scheme under Memari-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.4. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000492/2021-2022 | 179/BSD | 31/01/2022 | 02/03/2022 | RADIANT | 4.21 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10060 | Augmentation | Restoration work due to laying of 160 mm, 140 mm dia HDPE pipe along with Bardhaman Kalna Road from 31.00kmp to 32.00 kmp with sand filling, GSB, WBM & BM and shoulder portion jhama with moorum consolidation of Augmentation of Satgachia Zone-II water supply scheme "JAL JEEVAN MISSION" under Burdwan Division, PHE Dte. |  |  | BILL/00097/2023-2024 | 195/JJM | 31/05/2023 | 31/05/2023 | EXECUTIVE ENGINEER PWD BURDWAN DIVISION | 27.42 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10060 | Augmentation | Relaying of damaged pipeline of 90mm HDPE pipeline for FHTC work & shifiting of sluice valve chamber for Road culvert work from Zilla parisad at Satgachia zone-II Piped Water Supply Scheme within Memari-II block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000510/2024-2025 | 1857/BSD | 22/08/2024 | 21/09/2024 | D.M. ENTERPRISE | 0.93 | 0 | 0 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10060 | Augmentation | Different Types of work involved in connection with different Augmentation & Retrofitting Schemes (06 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001269/2024-2025 | 848/BWD | 05/03/2025 | 03/07/2025 | PROJECT INDIA | 394.29 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10060 | Augmentation | Extension of pipeline & providing Functional Household Tap Connection (350 Nos. FHTC) from existing distribution system within the command are of SATGACHIA Zone - II Piped W/S. Scheme at (Bohar, Jakra, Raibati) Mouza (14 Nos. Habitation) under Memari - II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000005/2023-2024 | 1681/BWD | 10/04/2023 | 25/05/2023 | G.B. CONSTRUCTION & CO. | 39.5 | 0 | 0 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10060 | Augmentation | Augmentation of SATGACHIA (Zone-II) Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 400 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation under Memari ¿ II Block, District - Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000005/2022-2023 | 1900/BWD | 07/04/2022 | 01/02/2025 | G.B. CONSTRUCTION & CO. | 391.54 | 0 | 0 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10060 | Augmentation | Replacement of Tube-well & Rising main at HEAD TW site for Aug. of PARHATI, SRIDHARPUR, SATGACHIA ZONE-I, SATGACHIA ZONE-II, Piped Water Supply Scheme within MEMARI-II Block under Burdwan Divn., PHE. Dte. District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000973/2023-2024 | 24/BWD | 03/01/2024 | 01/10/2025 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 54.2 | 0 | 0 | 90
Total | [13 empty] | 912.07 | 0 | 0