## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10061 | Augmentation | Route Survey & Preparation of DPR for Satgachia (Zone-I) & (Zone-II) W/S Scheme under Memari-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.4. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000492/2021-2022 | 179/BSD | 31/01/2022 | 02/03/2022 | RADIANT | 4.21 | 2.1 | 49.98 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10061 | Augmentation | Restoration work of Debipur-Bulbulitala Road from 15.00 km to 17.10 km (in stretches) damage due to laying of underground water pipeline by PHE with box cutting and jhama with moorum consolidation under Kalna Highway Sub-Division of Burdwan South Highway Division, P.W. Roads Dte. during the Year 2023-2024. |  |  | BILL/01173/2023-2024 | 1079/JJM | 20/12/2023 | 20/12/2023 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 5.51 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10061 | Augmentation | Construction of switch rooms & Rising main at different TW site for SATGACHIA (Zone-I) Piped Water Supply Scheme under Memari - II Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000535/2023-2024 | 3632/BWD | 21/08/2023 | 20/10/2023 | ROY ASSOCIATE | 9.08 | 7.65 | 84.29 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10061 | Augmentation | Different Types of work involved in connection with different Augmentation & Retrofitting Schemes (06 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001269/2024-2025 | 848/BWD | 05/03/2025 | 03/07/2025 | PROJECT INDIA | 394.29 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10061 | Augmentation | Replacement of Tube-well & Rising main at HEAD TW site for Aug. of PARHATI, SRIDHARPUR, SATGACHIA ZONE-I, SATGACHIA ZONE-II, Piped Water Supply Scheme within MEMARI-II Block under Burdwan Divn., PHE. Dte. District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000973/2023-2024 | 24/BWD | 03/01/2024 | 01/10/2025 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 54.2 | 14.26 | 26.31 | 90
6 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10061 | Augmentation | Repairing damaged Pipeline & concrete road by Cement concrete (mix 1:1.5:3) and drainage system, Sluice valve chamber for FHTC work for SATGACHIA ZONE-I, SATGACHIA ZONE-II, SRIDHARPUR, PARHATI, KUCHUT, NOAHATI, MONDALGRAM PWSS and its adjoining mouzas within MEMARI-II BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000283/2024-2025 | 2715/BWD | 11/07/2024 | 01/02/2025 | A.R. TRADERS | 74.28 | 4.83 | 6.51 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10061 | Augmentation | Augmentation of SATGACHIA (Zone-I) Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 500 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under MEMARI- II Block, District:- Purba-Burdwan. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000156/2022-2023 | 3123/BWD | 18/07/2022 | 01/10/2025 | M/S ASHA CONSTRUCTION | 544.27 | 421.18 | 77.39 | 85
Total | [13 empty] | 1085.83 | 450.03 | 41.45