## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Route Survey and Preparation of DPR for KETUGRAM (ZONE-I & II ) PWSS under Ketugram-I & II Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-06] | Assistant Engineer |  | ORD/000547/2021-2022 | 66/KTS | 27/01/2022 | 17/02/2022 | RADIANT | 4.81 | 4.91 | 102 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Ketugram (Zone - I) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000062/2023-2024 | 2569/CMD | 06/06/2023 | 06/07/2023 | M/S, MONDAL ASSOCIATES. | 10.98 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Supply , delivery & Installation of Submersible Pumping Machinery , Voltage stabiliser , Chlorinator and Internal House wiring for Tube well No. 3 of Kandra [ Ketugram ] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. [ Block - Ketugram-I ] | ASSISTANT ENGINEER |  | ORD/000007/2022-2023 | 1170/CMD | 27/06/2022 | 27/06/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 10.38 | 9.64 | 92.79 | 1
5 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-2 at Augmentation of Ketugram Water Supply Scheme [Zone-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER |  | ORD/000624/2022-2023 | 2098/CMD | 08/09/2022 | 08/10/2022 | STANDARD ELECTRICALS | 11.51 | 10.86 | 94.31 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Baharan-Birampur, Kaithan, Majhigram-Sigot & Ketugram (Zone-I & II) Piped Water Supply Scheme within Katwa Sub-Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000518/2022-2023 | 4702/BWD | 19/10/2022 | 08/11/2022 | SSPR VALVE MANUFACTURING PVT LTD. | 14.45 | 7.22 | 50 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000156/2021-2022 | 1248/BWD | 07/03/2022 | 07/03/2022 | Resource Division | 4.32 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000227/2021-2022 | 1549/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000176/2021-2022 | 1334/BWD | 08/03/2022 | 08/03/2022 | Resource Division | 114.05 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2022-2023 | 4631/BWD | 17/10/2022 | 17/10/2022 | Resource Division | 0.06 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 3271/BWD | 29/07/2022 | 29/07/2022 | Resource Division | 50.19 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Inter connection work with MS pipe from OHR to Distribution system and restoration of village road and drains for Augmentation of KETUGRAM Z-II Piped Water Supply Scheme under Ketugram-II Block, Dist-Purba Bardhaman. | Assistant Engineer | JE, Katwa Sub-Division | ORD/000909/2023-2024 | 5481/BWD | 13/12/2023 | 11/04/2024 | S & P ENTERPRISE | 181.31 | 77.21 | 42.58 | 40
13 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Sinking of additional 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Augmentation of KETUGRAM (ZONE-I) Piped Water Supply Scheme, Block - Ketugram - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000067/2022-2023 | 2420/BWD | 11/05/2022 | 25/06/2022 | AUXILIARY TUBE WELL DRILLERS | 23.9 | 20.87 | 87.32 | 100
14 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Quotation from WBSEDCL for new service connection of Augmentation of ground water based Ketugram Zone-I PWSS. |  |  | BILL/00516/2024-2025 | 688/JJM | 14/08/2024 | 14/08/2024 | WBSEDCL | 9.28 | 0 | 0 | 0
15 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Sinking of additional 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Augmentation of KETUGRAM (ZONE-II) Piped Water Supply Scheme, Block - Ketugram - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [3 Nos. GTW]. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000068/2022-2023 | 2421/BWD | 11/05/2022 | 31/12/2024 | AUXILIARY TUBE WELL DRILLERS | 35.85 | 18.19 | 50.74 | 80
16 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Augmentation of KETUGRAM ZONE-I (PART-A & PART-B) Piped Water Supply Scheme with LDS, FHTC, & Construction of 700 cum & 200 Cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation respectively under Ketugram-I Block, District:- Purba-Burdwan. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000149/2022-2023 | 3075/BWD | 11/07/2022 | 19/08/2025 | M/S S.S. ENTERPRISE | 930.6 | 737 | 79.2 | 70
17 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 3 at Augumentation of Ketugram (Zone - II) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000077/2023-2024 | 2573/CMD | 06/06/2023 | 06/07/2023 | SOUNAK ENTERPRISE | 21.96 | 0 | 0 | 40
18 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Augmentation of KETUGRAM ZONE-II Piped Water Supply Scheme with LDS, FHTC, & Construction of 1250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under Ketugram-II Block, District:- Purba-Burdwan. | Assistant Engineer | JE, Katwa Sub-Division,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000125/2022-2023 | 2996/BWD | 05/07/2022 | 01/12/2024 | S & P ENTERPRISE | 1064.91 | 965.35 | 90.65 | 90
19 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Continuation work order for Supply of 1 (one) No. Diesel driven Ambassador Car (Luxury Taxi) / Motor Cab on hire basis for the Office of the Assistant Engineer, under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.01.2025 to 30.06.2025]. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/001026/2024-2025 | 1810/KTS | 31/12/2024 | 30/06/2025 | KRISHNA MONDAL | 2.4 | 1.17 | 48.84 | 20
20 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10085 | Augmentation | Balance Work For OHR, Extension Of Pipeline To Provide FHTC With Sinking Of Tube Well, Construction Of Pump House, Boundary Wall, Land Development, Plinth Protection For Pump House, Approach Road & Other Related Work Under Bakalsa, Chakdaha, Ehaipur, Khatundi And Ketugram (Zone-I) Part-A & B PWSS Under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000288/2024-2025 | 2741/BWD | 12/07/2024 | 31/08/2025 | M/S M.M. ENTERPRISE | 205.15 | 0 | 0 | 65
Total | [13 empty] | 5701.5 | 1852.41 | 32.49