## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10123 | Augmentation | Route Survey and Preparation of DPR for MOUGRAM (ZONE-I & II) PWSS under Ketugram-II Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-07] | Assistant Engineer |  | ORD/000548/2021-2022 | 67/KTS | 27/01/2022 | 17/02/2022 | RADIANT | 4.11 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10123 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10123 | Augmentation | Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day.(Sl No-1) |  |  | ORD/000510/2023-2024 | 499/KTS | 22/05/2023 | 31/07/2023 | M/S MUNMUN DEY | 0.9 | 0 | 0 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10123 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000189/2021-2022 | 1383/BWD | 09/03/2022 | 09/03/2022 | Resource Division | 4.47 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10123 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000177/2021-2022 | 1335/BWD | 08/03/2022 | 08/03/2022 | Resource Division | 25.88 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10123 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000229/2021-2022 | 1551/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10123 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 3280/BWD | 29/07/2022 | 29/07/2022 | Resource Division | 34.57 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10123 | Augmentation | Shifting of 63 KVA DTR at Naliapur village of Augmentation of Mougram Z-II water supply scheme under Burdwan Division, PHE Dte. (Ref ID-860268576, Application ID-100000077306, dt.-02/05/2023) |  |  | BILL/00142/2023-2024 | 231/JJM/23-24 | 13/06/2023 | 13/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.21 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10123 | Augmentation | Continuation order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day. (Sl No-1) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000930/2023-2024 | 1016/KTS | 20/09/2023 | 13/10/2023 | M/S MUNMUN DEY | 0.3 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10123 | Augmentation | Augmentation of MOUGRAM (ZONE-I) Piped Water Supply Scheme with LDS, FHTC, & Construction of 250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under Ketugram-II Block, District:- Purba-Burdwan. | Assistant Engineer | Junior Engineer, R.W.S., Katwa-I Dev. Block | ORD/000087/2022-2023 | 2611/BWD | 23/05/2022 | 23/05/2023 | UMWELT ENGINEER PVT LTD | 499.84 | 0 | 0 | 97
Total | [13 empty] | 3579.65 | 0 | 0