## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for 3rd TW Site of Aug. KAITY & its adjoining mouzas Piped Water Supply Scheme, Block ¿ Raina ¿ II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000569/2022-2023 | 5281/BWD | 01/12/2022 | 31/12/2022 | MUNSHI ENTERPRISE | 11.34 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Augmentation of KAITY Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 700 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under RAINA- II Block, District:- Purba-Burdwan. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000124/2022-2023 | 2930/BWD | 28/06/2022 | 28/06/2023 | SK ALIM | 689.36 | 688.91 | 99.93 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Route Survey & Preparation of DPR for Kaity W/S Scheme under Raina-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.16. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000505/2021-2022 | 191/BSD | 31/01/2022 | 02/03/2022 | RADIANT | 3.43 | 3.42 | 99.6 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of KAITY & its adjoining mouzas Piped Water Supply Scheme, Block - Raina - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000538/2022-2023 | 5026/BWD | 10/11/2022 | 10/12/2022 | M/S D. PALIT & CO. | 10.06 | 8.33 | 82.75 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000190/2021-2022 | 1385/BWD | 09/03/2022 | 09/03/2022 | Resource Division | 4.26 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000228/2021-2022 | 1550/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Quotation for shifting of 25 KVA DTR along with 11 KV HTOH Kaity Feeder at Kaity PHE campus under Madhabdihi-CCC. [Ref Id-860252403] |  |  | VCH/000627/2022-2023 | 726/DW/22-23 | 03/11/2022 | 03/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.71 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Allied works for Augmentation of KAITY W/S Scheme under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000345/2023-2024 | 3034/BWD | 14/07/2023 | 12/10/2023 | SK ALIM | 122.65 | 114.07 | 93 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for KAITY its Adjoining Mouza W/S Scheme, Block -Raina-II within Burdwan Sub-Division, PHE Dte. (Mouza- DURGABATI) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000768/2022-2023 | 503/BSD | 21/03/2023 | 05/05/2023 | DEBJYOTI GOSWAMI | 3.61 | 2.85 | 78.93 | 100
11 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring of Tube Well No- 01 & 02 at Augmentation Kaity [Block ¿Raina-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000918/2022-2023 | 1082/CMD | 03/03/2023 | 02/04/2023 | JOYGURU ENTERPRISE | 12.31 | 11.96 | 97.16 | 100
12 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Installation of Electro-mechanical accessories at Kaity PH-1 (replacement T.W) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000993/2023-2024 | 4352/CMD | 20/09/2023 | 20/10/2023 | MITRA ENTERPRISE | 3.28 | 3.28 | 100 | 100
13 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | 02 Nos. Quotation for new connection of WBSEDCL of Augmentation of Kaity water supply scheme. |  |  | BILL/00195/2023-2024 | 302/JJM/23-24 | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 12.21 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | AE(HQs),Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 01/04/2026 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 0 | 85
15 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Laying Distribution for FHTC work including laying of parallel line for KAITY Piped Water Supply Scheme and its adjoining mouzas within RAINA-II BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001029/2024-2025 | 143/BWD | 08/01/2025 | 01/01/2026 | M/S ANAND CONSTRUCTION | 19.77 | 0 | 0 | 55
16 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Bhanjapur village of Raina-II Block under Kaity Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000428/2025-2026 | 1206/BSD | 22/05/2025 | 01/06/2025 | AIRC CONSTRUCTION (OPC) PVT. LTD. | 0.73 | 0 | 0 | 100
17 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Gobindapur village of Raina-II Block under Kaity Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte (5 nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000522/2025-2026 | 1323/BSD | 05/06/2025 | 15/06/2025 | AIRC CONSTRUCTION (OPC) PVT. LTD. | 0.73 | 0 | 0 | 100
18 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Maszidpur village of Raina-II Block under Kaity Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte(5 nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000520/2025-2026 | 1195/BSD | 22/05/2025 | 01/06/2025 | AIRC CONSTRUCTION (OPC) PVT. LTD. | 0.72 | 0 | 0 | 100
19 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Nasipur village of Raina-II Block under Kaity Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte (5 nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000502/2025-2026 | 1204/BSD | 22/05/2025 | 01/06/2025 | AIRC CONSTRUCTION (OPC) PVT. LTD. | 0.72 | 0 | 0 | 100
20 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Durgabati village of Raina-II Block under Kaity Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte(5 nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000479/2025-2026 | 1228/BSD | 27/05/2025 | 06/06/2025 | AIRC CONSTRUCTION (OPC) PVT. LTD. | 0.73 | 0 | 0 | 100
21 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | SM/10130 | Augmentation | Designing,making and erection of Sign Board for SWAJAL GRAM in Kurchigara village of Raina-II Block under Kaity Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte. (5 Nos. Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000432/2025-2026 | 1207/BSD | 22/05/2025 | 01/06/2025 | AIRC CONSTRUCTION (OPC) PVT. LTD. | 0.73 | 0 | 0 | 100
Total | [13 empty] | 4213.3 | 832.82 | 19.77