## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10337 | Augmentation | Preparation of DPR for augmentation of Hatkalna W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-C) | Assistant Engineer |  | ORD/000610/2021-2022 | 269/KSD | 15/03/2022 | 05/04/2022 | ROY CHOWDHURY ASSOCIATES | 3.23 | 3.22 | 99.65 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10337 | Augmentation | Sinking of Tube well 250 x 200 mm dia Tube well 150 mtr depth by D.R. Rig method using UPVC pipe (CD) and fibre glass strainer for HATKALNA piped water supply scheme (2nd tube well site), Block-Kalna-I, Dist.-Purba Bardhaman, under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000962/2020-2021 | 1492/BWD | 18/02/2021 | 20/03/2021 | C.M. ENTERPRISE | 8.68 | 8.06 | 92.75 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10337 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for 2nd TW Site of Aug. HATKALNA & its adjoining mouzas Piped Water Supply Scheme, Block ¿ Kalna ¿ I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000699/2022-2023 | 605/BWD | 17/02/2023 | 19/03/2023 | AUXILIARY TUBE WELL DRILLERS | 8.64 | 8.44 | 97.69 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10337 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 3279/BWD | 29/07/2022 | 29/07/2022 | Resource Division | 52.8 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10337 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 3RD TW Site of Aug. HATKALNA & its adjoining mouzas Piped Water Supply Scheme, Block ¿ Kalna ¿ I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 01 No. Tube well]. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000218/2023-2024 | 2711/BWD | 08/06/2023 | 08/07/2023 | AUXILIARY TUBE WELL DRILLERS | 9.89 | 9.34 | 94.38 | 90
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10337 | Augmentation | Additional work viz. Carriage of different type of departmental pipes and Interconnection of Tube well and existing pipe line and Restoration of existing concrete road and laying of pipeline of HATKALNA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000969/2023-2024 | 003/BWD | 02/01/2024 | 01/05/2024 | S.P. CONSTRUCTION | 162.05 | 161.21 | 99.48 | 100
7 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10337 | Augmentation | Supply & Installation of Chlorination System for Tube well No.-1 at Hat Kalna Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001866/2023-2024 | 464/CMSD | 21/03/2024 | 02/04/2024 | JOYGURU ENTERPRISE | 0.96 | 0.96 | 100 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10337 | Augmentation | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 11 Nos. Piped W/S. Schemes under Kalna I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000335/2024-2025 | 3015/BWD | 05/08/2024 | 04/10/2024 | HORIZEN | 29.6 | 11.1 | 37.5 | 10
9 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10337 | Augmentation | Supply & Installation of Chlorination System for Tube well No.-2 at Hat Kalna Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001847/2023-2024 | 377/CMSD | 29/02/2024 | 15/03/2024 | SUDIKSHA CONSTRUCTION | 0.96 | 0.96 | 100 | 100
10 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10337 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT AUGMENTATION OF HAT KALNA PWSS TW 3, BLOCK KALNA-1 |  |  | BILL/00727/2024-2025 | BP-2024-25-285 | 10/09/2024 | 10/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.36 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10337 | Augmentation | Augmentation of Hatkalna Piped Water Supply Scheme with LDS, FHTC, Construction of 1000 cum capacity OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site & repairing of switch rooms under Kalna-I Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000536/2022-2023 | 5019/BWD | 10/11/2022 | 02/10/2025 | S.P. CONSTRUCTION | 976.48 | 858.64 | 87.93 | 50
12 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10337 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring of Tube Well No- 01,02 03 & 04 at Augmentation Hatkalna [Block -Kalna-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000916/2022-2023 | 1080/CMD | 03/03/2023 | 31/05/2025 | P.K. ENGINEERING | 41.64 | 0 | 0 | 35
13 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10337 | Augmentation | Construction of switch rooms & Rising main at different TW site for Hatkalna Piped Water Supply Scheme under Kalna - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000757/2023-2024 | 4736/BWD | 03/11/2023 | 29/12/2024 | BISWAS ENTERPRISE | 8.38 | 0 | 0 | 100
14 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10337 | Augmentation | Construction of 1.5 Mtr. height boundary wall along with 750 mm. height 3 layer barbed wire and other ancillary works at Head Work Site in connection with Augmentation of Hatkalna PWSS (SM/10337) Piped Water Supply Scheme within Kalna Sub Division under Burdwan Divn., PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000813/2024-2025 | 4067/BWD | 21/11/2024 | 21/12/2024 | UJJWAL MUKHERJEE | 20.99 | 0 | 0 | 100
15 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10337 | Augmentation | Work Order for "Construction of Toilet (1.8 m x 1.8 m) with saitary arrangement in connection with Augmentation of Hatkalna pwss (SM/10337) under Kalna sub division under Burdwan Division." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000796/2024-2025 | 1766/KSD | 20/11/2024 | 20/12/2024 | S.B.S. ENTERPRISE | 4.91 | 0 | 0 | 100
16 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10337 | Augmentation | Work Order for "Constrcution of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire in connection with Augmentation of Hatkalna PWSS ( SM/10337) Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000798/2024-2025 | 1767/KSD | 20/11/2024 | 20/12/2024 | S.B.S. ENTERPRISE | 3.35 | 2.89 | 86.23 | 2
17 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10337 | Augmentation | Renovation of Pump House in connection with Augmentation of Hatkalna piped Water supply (SM/10337) Scheme under Kalna Sub-Division under Burdwan Division, PHE Dte. (2 units) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000746/2024-2025 | 3747/BWD | 29/10/2024 | 28/11/2024 | S.B.S. ENTERPRISE | 9.7 | 8.76 | 90.36 | 100
18 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10337 | Augmentation | Work Order for "Constrcution of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around Other than head work site for Hatkalna Piped Water Supply Scheme (SM/10337) within Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001185/2023-2024 | 2188/KSD | 15/03/2024 | 23/07/2024 | BISWAS ENTERPRISE | 4.59 | 0 | 0 | 100
Total | [13 empty] | 1353.22 | 1073.58 | 79.34