## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/10391 | Augmentation | Construction of 600 cum capacity 20 mtr staging height RCC Over Head Reservoir including pipe connection and cost of pipes, specials for Bonpass-Kamarpara & its adjoining mouzas water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000727/2021-2022 | 3655/BWD | 14/07/2021 | 10/01/2022 | ASHOK MITRA | 107 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/10391 | Augmentation | Sinking of additional 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 4th & 5th Tube well Site for Augmentation of BONPAS-KAMARPARA Piped Water Supply Scheme, Block - Bhatar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000141/2022-2023 | 3031/BWD | 07/07/2022 | 21/08/2022 | B.K. ENTERPRISE | 28.13 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/10391 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 5 at BonpassKamarpara Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000765/2022-2023 | 3329/CMD | 12/12/2022 | 11/01/2023 | CHOUDHURY ENTERPRISE | 10.09 | 9.82 | 97.27 | 100
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/10391 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 4 at BonpassKamarpara Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000764/2022-2023 | 3328/CMD | 12/12/2022 | 11/01/2023 | P.K. ENGINEERING | 10.06 | 9.65 | 95.92 | 80
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/10391 | Augmentation | Augmentation of BANPAS Piped Water Supply Scheme (Dhandalsa Mouza) with LDS & FHTC and construction of Pump House at 4th TW site under Bhatar Block, District:- Purba-Burdwan under Burdwan Division, PHE. Dte. [PART-F]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000716/2022-2023 | 891/BWD | 01/03/2023 | 30/04/2023 | DEY NIRMAN | 71.08 | 71.08 | 100 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/10391 | Augmentation | Repairing of Switch room cum chlorine room with sanitary and water supply arrangement (P.H-2) at 2nd Tubewell Site for Bonpas-Kamarpara and its adjoining mouza's water supply scheme under Durgapur Sub-Division, P.H.E Dte. Block:-Bhatar, Dist:Purba Bardhaman. [Gr.-F] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000274/2022-2023 | 499/DSD | 12/08/2022 | 11/09/2022 | SUPRIYA RAY | 2.03 | 0 | 0 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/10391 | Augmentation | Augmentation of BANPAS KAMARPARA Piped Water Supply Scheme (Haribati & Chandai Mouza) with LDS & FHTC within Bhatar Block, District:- Purba-Burdwan under Burdwan Division, PHE. Dte. [PART-E]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000103/2023-2024 | 2262/BWD | 18/05/2023 | 17/07/2023 | M/S K.P. CONSTRUCTION | 80.02 | 57.31 | 71.62 | 80
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/10391 | Augmentation | Augmentation of BANPAS Piped Water Supply Scheme (Narayanpur Mouza) with LDS, FHTC and Construction of Pump House at 4th TW site under Bhatar Block, District:- Purba-Burdwan under Burdwan Division, PHE. Dte. [PART-D]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000728/2022-2023 | 1029/BWD | 09/03/2023 | 08/05/2023 | SARKAR AGENCY | 111.93 | 111.2 | 99.35 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/10391 | Augmentation | Augmentation of BANPAS KAMARPARA Piped Water Supply Scheme (Ambana Mouza) with LDS, FHTC and Construction of Pump House at 4th TW site under Bhatar Block, District:- Purba-Burdwan under Burdwan Division, PHE. Dte. [PART-B]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000102/2023-2024 | 2261/BWD | 18/05/2023 | 17/07/2023 | M/S K.P. CONSTRUCTION | 91.92 | 88.24 | 96 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/10391 | Augmentation | Augmentation of BONPAS KAMARPARA Piped Water Supply Scheme (Banpas Mouza) with LDS, Rising main, FHTC and construction of Boundary wall for existing TW site under Bhatar Block, District:- Purba-Burdwan. (PART - A) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000376/2023-2024 | 3110/BWD | 19/07/2023 | 16/11/2023 | R.G. INFRASTRUCTURE | 389.91 | 312.73 | 80.21 | 80
11 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/10391 | Augmentation | Augmentation of BANPAS Piped Water Supply Scheme (Mohanpur Mouza) with LDS & FHTC under Bhatar Block, District:- Purba-Burdwan under Burdwan Division, PHE. Dte. [PART-C]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000713/2022-2023 | 888/BWD | 01/03/2023 | 30/04/2023 | KOUSIK MALLICK | 104.59 | 106.42 | 101.75 | 100
12 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/10391 | Augmentation | Illumination arrangement and miscelleneous works at Bonpas Kamarpara water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000406/2024-2025 | 2785/CMD | 01/10/2024 | 30/11/2024 | CINZANO | 14.08 | 0 | 0 | 50
Total | [13 empty] | 1020.84 | 766.46 | 75.08