## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Route Survey & Preparation of DPR for Borsul (Zone-I) & (Zone-II) W/S Scheme under Burdwan-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.1. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000510/2021-2022 | 176/BSD | 31/01/2022 | 02/03/2022 | APEX ENGINEERING | 4.18 | 4.18 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BELNA Mouza & Head Works Site for BORSHUL (Zone-II) Piped Water Supply Scheme, Block - Burdwan - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 02 Nos. Tube well]. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000206/2023-2024 | 2709/BWD | 08/06/2023 | 23/07/2023 | M/S D. PALIT & CO. | 19.82 | 17.8 | 89.8 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2022-2023 | 4852/BWD | 20/10/2022 | 20/10/2022 | Resource Division | 12.32 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | New service connection charges for Borshul PWSS Z-II TW-1 |  |  | BILL/01414/2023-2024 | BP-2023-24-140 | 28/08/2023 | 28/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.99 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Improvement works of Borshul Godown & other allied works under Augmentation of BORSHUL (Zone-II) PWSS in Bardhaman-II Block. (SM/10481) within Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000187/2024-2025 | 2418/BWD | 27/06/2024 | 25/09/2024 | ANWESHA CONSTRUCTION | 20.86 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for BARSUL ZONE-II its Adjoining Mouza W/S Scheme, Block -BURDWAN-II within Burdwan Sub-Division, PHE Dte. (Mouza- Belna) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000772/2022-2023 | 509/BSD | 21/03/2023 | 05/05/2023 | MOHAMMAD ISSA | 3.49 | 2.89 | 82.76 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Construction of 3.6mtr.x3.0mtr.Size pump house including plinth protection with surface drain at Head Work TW site for Borshul (Zone-II) Water Supply Scheme, Block: Burdwan-II within Burdwan Division, PHE Dte. Dist.-Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000589/2023-2024 | 2042/BSD | 24/08/2023 | 08/10/2023 | RAHAMAN ENTERPRISE | 4.84 | 4.84 | 100 | 100
8 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | New service connection charges for Borshul PWSS ZONE-II, TW-2 |  |  | BILL/01827/2023-2024 | BP-2023-24-335 | 06/01/2024 | 06/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.11 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Quotation for new service connection at Borsul W/S Scheme Zone-II, PH-III. |  |  | BILL/00862/2024-2025 | BP-2024-25-334 | 04/10/2024 | 04/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.86 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Augmentation of Borshul (Zone-II) (Mouzas :- Belna, Manikhati, Jafrabad, Kalinagar, Baje Salepur, Totopara) Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under BARDHAMAN- II Block, District:- Purba-Burdwan. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000151/2022-2023 | 3101/BWD | 14/07/2022 | 28/12/2024 | ASHOK KUMAR GHOSH | 342.55 | 311.53 | 90.94 | 80
11 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring of Tube Well No- 01, 02 & 03 at Augmentation Borsul (Zone-II) [Block ¿Burdwan -2] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000914/2023-2024 | 4178/CMD | 29/08/2023 | 01/01/2025 | M/S, S.S. ENTERPRISE. | 35.95 | 23.47 | 65.29 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Construction of boundary wall at 2nd T/W Site (Belna-Mouza) of BARSUL Zone II Piped W/S. Scheme under Burdwan-II Block of Burdwan Division, PHE Dte. (Length =100.00 Mtr, Col-36 Nos). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000487/2024-2025 | 3142/BWD | 20/08/2024 | 01/01/2025 | PANCHANAN CHAKROBORTY | 6.77 | 0 | 0 | 100
13 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Improvement works including repairing & remodelling of Borshul Inspection Banglow under Augmentation of BORSHUL (Zone-II) PWSS in Bardhaman-II Block. (SM/10481) within Burdwan Division PHE Dte. | AE(HQs),ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | J.E. 1 BURDWAN | ORD/000285/2024-2025 | 2971/BWD | 31/07/2024 | 29/10/2024 | ESCON INDIA | 15.27 | 0 | 0 | 100
14 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Construction of switch room, rising main & Sinking of Tube-well at 3rd TW SITE for BARSHUL Zone-II Piped Water Supply Scheme under BARDHAMAN-II Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/001101/2023-2024 | 1128/BWD | 14/03/2024 | 31/12/2024 | M/S R.K. SAMANTA & CO. | 19.02 | 0 | 0 | 100
15 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Construction of boundary wall at 1ST TUBE WALL (HEAD WORK) Site of BARSUL Zone-II Piped W/S. Scheme under Burdwan-II Block of Burdwan Division, PHE Dte. (Length =174.00 Mtr, Col-65 Nos). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000227/2024-2025 | 2521/BWD | 03/07/2024 | 31/12/2024 | RAHAMAN ENTERPRISE | 13.25 | 0 | 0 | 100
Total | [13 empty] | 515.26 | 364.7 | 70.78