## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Augmentation of Borshul (Zone-II) (Mouzas :- Belna, Manikhati, Jafrabad, Kalinagar, Baje Salepur, Totopara) Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under BARDHAMAN- II Block, District:- Purba-Burdwan. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000151/2022-2023 | 3101/BWD | 14/07/2022 | 28/12/2024 | ASHOK KUMAR GHOSH | 342.55 | 311.53 | 90.94 | 80
2 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Route Survey & Preparation of DPR for Borsul (Zone-I) & (Zone-II) W/S Scheme under Burdwan-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.1. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000510/2021-2022 | 176/BSD | 31/01/2022 | 02/03/2022 | APEX ENGINEERING | 4.18 | 4.18 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2022-2023 | 4852/BWD | 20/10/2022 | 20/10/2022 | Resource Division | 12.32 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Construction of 3.6mtr.x3.0mtr.Size pump house including plinth protection with surface drain at Head Work TW site for Borshul (Zone-II) Water Supply Scheme, Block: Burdwan-II within Burdwan Division, PHE Dte. Dist.-Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000589/2023-2024 | 2042/BSD | 24/08/2023 | 08/10/2023 | RAHAMAN ENTERPRISE | 4.84 | 4.84 | 100 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for BARSUL ZONE-II its Adjoining Mouza W/S Scheme, Block -BURDWAN-II within Burdwan Sub-Division, PHE Dte. (Mouza- Belna) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000772/2022-2023 | 509/BSD | 21/03/2023 | 05/05/2023 | MOHAMMAD ISSA | 3.49 | 2.89 | 82.76 | 100
6 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring of Tube Well No- 01, 02 & 03 at Augmentation Borsul (Zone-II) [Block ¿Burdwan -2] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000914/2023-2024 | 4178/CMD | 29/08/2023 | 01/01/2025 | M/S, S.S. ENTERPRISE. | 35.95 | 23.47 | 65.29 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BELNA Mouza & Head Works Site for BORSHUL (Zone-II) Piped Water Supply Scheme, Block - Burdwan - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 02 Nos. Tube well]. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000206/2023-2024 | 2709/BWD | 08/06/2023 | 23/07/2023 | M/S D. PALIT & CO. | 19.82 | 17.8 | 89.8 | 100
8 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | New service connection charges for Borshul PWSS Z-II TW-1 |  |  | BILL/01414/2023-2024 | BP-2023-24-140 | 28/08/2023 | 28/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.99 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Improvement works of Borshul Godown & other allied works under Augmentation of BORSHUL (Zone-II) PWSS in Bardhaman-II Block. (SM/10481) within Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000187/2024-2025 | 2418/BWD | 27/06/2024 | 25/09/2024 | ANWESHA CONSTRUCTION | 20.86 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | AE(HQs),Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 01/04/2026 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 0 | 85
11 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Construction of switch room, rising main & Sinking of Tube-well at 3rd TW SITE for BARSHUL Zone-II Piped Water Supply Scheme under BARDHAMAN-II Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/001101/2023-2024 | 1128/BWD | 14/03/2024 | 31/12/2024 | M/S R.K. SAMANTA & CO. | 19.02 | 0 | 0 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Improvement works including repairing & remodelling of Borshul Inspection Banglow under Augmentation of BORSHUL (Zone-II) PWSS in Bardhaman-II Block. (SM/10481) within Burdwan Division PHE Dte. | AE(HQs),ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | J.E. 1 BURDWAN | ORD/000285/2024-2025 | 2971/BWD | 31/07/2024 | 29/10/2024 | ESCON INDIA | 15.27 | 0 | 0 | 100
13 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Construction of boundary wall at 1ST TUBE WALL (HEAD WORK) Site of BARSUL Zone-II Piped W/S. Scheme under Burdwan-II Block of Burdwan Division, PHE Dte. (Length =174.00 Mtr, Col-65 Nos). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000227/2024-2025 | 2521/BWD | 03/07/2024 | 31/12/2024 | RAHAMAN ENTERPRISE | 13.25 | 0 | 0 | 100
14 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Construction of boundary wall at 2nd T/W Site (Belna-Mouza) of BARSUL Zone II Piped W/S. Scheme under Burdwan-II Block of Burdwan Division, PHE Dte. (Length =100.00 Mtr, Col-36 Nos). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000487/2024-2025 | 3142/BWD | 20/08/2024 | 01/01/2025 | PANCHANAN CHAKROBORTY | 6.77 | 0 | 0 | 100
15 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | New service connection charges for Borshul PWSS ZONE-II, TW-2 |  |  | BILL/01827/2023-2024 | BP-2023-24-335 | 06/01/2024 | 06/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.11 | 0 | 0 | 0
16 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Quotation for new service connection at Borsul W/S Scheme Zone-II, PH-III. |  |  | BILL/00862/2024-2025 | BP-2024-25-334 | 04/10/2024 | 04/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.86 | 0 | 0 | 0
17 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Totpara village of Burdwan-II Block under Barsul Z: II Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte (5 nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000611/2025-2026 | 2354/BSD | 21/08/2025 | 31/08/2025 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.72 | 0 | 0 | 100
18 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Construction of internal pathway , approch road and Ohr Plinth protection at head work site for Borshul Z-II PWSS under Bardhaman-II block within Burdwan Div.PHE Dte. |  | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000654/2025-2026 | 1411/BSD | 17/06/2025 | 16/08/2025 | RADHAKRISHNA ENTERPRISE | 4.6 | 0 | 0 | 100
19 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Designing,making and erection of Sign Board for SWAJAL GRAM in Baje Salepur village of Burdwan-II Block under Barshul (Zone-II) Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte (5 Nos. Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000448/2025-2026 | 2311/BSD | 19/08/2025 | 29/08/2025 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.72 | 0 | 0 | 100
20 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | SM/10481 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Belna village of Burdwan-II Block under Barsul-II Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte(5 nos. Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000467/2025-2026 | 2333/BSD | 21/08/2025 | 31/08/2025 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.72 | 0 | 0 | 100
Total | [13 empty] | 831.63 | 364.7 | 43.85