## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(290 nos) for 100% School Coverage in Purba Bardhaman within Kalna Sub Division under Burdwan Division P.H.E. DTE. | SM/11283 | School | Material Requisition To Resource Division |  |  | RTOR000049/2022-2023 | 5398/BWD | 12/12/2022 | 12/12/2022 | Resource Division | 85 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(290 nos) for 100% School Coverage in Purba Bardhaman within Kalna Sub Division under Burdwan Division P.H.E. DTE. | SM/11283 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Purbasthali II Block (16 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000289/2022-2023 | 3595/BWD | 17/08/2022 | 16/09/2022 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 17.9 | 16.44 | 91.81 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(290 nos) for 100% School Coverage in Purba Bardhaman within Kalna Sub Division under Burdwan Division P.H.E. DTE. | SM/11283 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Monteswar Block (47 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-C). | Assistant Engineer |  | ORD/000324/2022-2023 | 3661/BWD | 29/08/2022 | 13/10/2022 | MITHU BUILDERS | 52.73 | 45.16 | 85.65 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(290 nos) for 100% School Coverage in Purba Bardhaman within Kalna Sub Division under Burdwan Division P.H.E. DTE. | SM/11283 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Kalna-I Block (43 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte._2ND CALL. | Assistant Engineer |  | ORD/000363/2022-2023 | 3806/BWD | 02/09/2022 | 17/10/2022 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 48.36 | 42.83 | 88.57 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(290 nos) for 100% School Coverage in Purba Bardhaman within Kalna Sub Division under Burdwan Division P.H.E. DTE. | SM/11283 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Purbasthali ¿ I Block (36 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000192/2022-2023 | 3418/BWD | 05/08/2022 | 04/09/2022 | HAMID SK | 40.56 | 36.13 | 89.09 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(290 nos) for 100% School Coverage in Purba Bardhaman within Kalna Sub Division under Burdwan Division P.H.E. DTE. | SM/11283 | School | Material Requisition To Resource Division |  |  | RTOR000025/2022-2023 | 3300/BWD | 29/07/2022 | 29/07/2022 | Resource Division | 104.7 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(290 nos) for 100% School Coverage in Purba Bardhaman within Kalna Sub Division under Burdwan Division P.H.E. DTE. | SM/11283 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Monteswar Block (50 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-B). | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000306/2022-2023 | 3665/BWD | 29/08/2022 | 13/10/2022 | SUKALPA NIRMAN | 56.36 | 51.46 | 91.3 | 50
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(290 nos) for 100% School Coverage in Purba Bardhaman within Kalna Sub Division under Burdwan Division P.H.E. DTE. | SM/11283 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Monteswar Block (50 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-A). | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000307/2022-2023 | 3662/BWD | 29/08/2022 | 13/10/2022 | SUPRIYA RAY | 56.36 | 51.31 | 91.03 | 100
Total | [13 empty] | 461.97 | 243.33 | 52.67