## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. | SM/11284 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Galsi I Block (42 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-A). | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000299/2022-2023 | 3663/BWD | 29/08/2022 | 13/10/2022 | SAIKAT RAY | 47.35 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. | SM/11284 | School | Material Requisition To Resource Division |  |  | RTOR000050/2022-2023 | 5397/BWD | 12/12/2022 |  | Resource Division | 85 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. | SM/11284 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Galsi ? II Block (40 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-B). | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000298/2022-2023 | 3608/BWD | 18/08/2022 | 02/10/2022 | GENUINE ENGINEERING CO-OP. SOCIETY LTD. | 45.08 | 36.13 | 80.15 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. | SM/11284 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Ausgram ? I Block (27 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000290/2022-2023 | 3596/BWD | 17/08/2022 | 01/10/2022 | SIRAJUL MANDAL | 29.87 | 28.74 | 96.2 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. | SM/11284 | School | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 3299/BWD | 29/07/2022 |  | Resource Division | 80.44 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. | SM/11284 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Ausgram ? II Block (31 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-A). | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000344/2022-2023 | 3691/BWD | 29/08/2022 | 13/10/2022 | BASUNDHARA SOLUTION | 34.6 | 24.57 | 71 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. | SM/11284 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Bhatar Block (40 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000194/2022-2023 | 3417/BWD | 05/08/2022 | 19/09/2022 | DHIRENDRANATH SOM | 45.05 | 32.84 | 72.89 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. | SM/11284 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Galsi ¿ I Block (41 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-B). | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000308/2022-2023 | 3664/BWD | 29/08/2022 | 13/10/2022 | ASHOK KUMAR GHOSH | 46.23 | 29.07 | 62.89 | 100
Total | [13 empty] | 413.62 | 151.34 | 36.59