## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. | SM/11285 | School | Material Requisition To Resource Division |  |  | RTOR000051/2022-2023 | 5399/BWD | 12/12/2022 | 12/12/2022 | Resource Division | 85 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. | SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Raina II Block (39 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-B). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000301/2022-2023 | 3634/BWD | 23/08/2022 | 07/10/2022 | PREMANANDA ROY BISWAS | 43.83 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. | SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Memari ¿ I Block (17 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000191/2022-2023 | 3415/BWD | 05/08/2022 | 04/09/2022 | DIPAYAN DEY | 17.85 | 0 | 0 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. | SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Raina I Block (34 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-A)_2ND CALL. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000329/2022-2023 | 3673/BWD | 29/08/2022 | 13/10/2022 | MOTI RAHAMAN | 37.97 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. | SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Burdwan-I Block (37 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000196/2022-2023 | 3419/BWD | 05/08/2022 | 19/09/2022 | P.C. CONSTRUCTION | 41.51 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. | SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Khandaghosh Block (43 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-A). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000343/2022-2023 | 3690/BWD | 29/08/2022 | 13/10/2022 | SHUBHRA KANTI GHOSH | 48.43 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. | SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Khandaghosh Block (43 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-B). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000302/2022-2023 | 3666/BWD | 29/08/2022 | 13/10/2022 | M/S LOKE NIRMAN | 48.38 | 0 | 0 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. | SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Raina ¿ II Block (34 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-A). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000281/2022-2023 | 3612/BWD | 18/08/2022 | 02/10/2022 | HAFIJUR RAHAMAN MIDYA | 43.97 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. | SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Jamalpur Block (05 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000279/2022-2023 | 3588/BWD | 17/08/2022 | 01/09/2022 | UDYOG CONSTRUCTION | 4.72 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. | SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Raina I Block (33 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-B). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000193/2022-2023 | 3416/BWD | 05/08/2022 | 19/09/2022 | THREE MAA ENTERPRISE | 36.46 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. | SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Burdwan-II Block (28 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000195/2022-2023 | 3414/BWD | 05/08/2022 | 19/09/2022 | G.S. CONSTRUCTION & CO. | 31.49 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. | SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Memari II Block (41 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000300/2022-2023 | 3636/BWD | 23/08/2022 | 07/10/2022 | BRINDABAN KONAR | 46.23 | 0 | 0 | 100
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. | SM/11285 | School | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 3298/BWD | 29/07/2022 | 29/07/2022 | Resource Division | 90.49 | 0 | 0 | 0
Total | [13 empty] | 576.33 | 0 | 0