## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Jamalpur | Burdwan Division | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | Material Requisition To Resource Division |  |  | RTOR000053/2022-2023 | 5522/BWDQ | 23/12/2022 | 23/12/2022 | Resource Division | 8.88 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Jamalpur | Central Mechanical | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 at Kalera Water Supply Scheme [ Block- Jamalpur ] under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000609/2022-2023 | 3115/CMD | 23/11/2022 | 23/12/2022 | P.K. ENGINEERING | 11.07 | 10.73 | 96.94 | 80
3 | PURBA BARDHAMAN | Jamalpur | Central Mechanical | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-2 at Kalera Water Supply Scheme [ Block- Jamalpur ] under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000610/2022-2023 | 3116/CMD | 23/11/2022 | 23/12/2022 | DUTTA ENTERPRISE | 11.08 | 7.74 | 69.84 | 80
4 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY DEPARTMENTAL RIG MACHINE FOR KALERA W/S (TW-I) SCH, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. |  |  | ORD/000288/2022-2023 | 319/CMSD-I | 21/07/2022 | 05/08/2022 | C.M. ENTERPRISE | 1.74 | 1.74 | 100 | 1
5 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KALERA W/S (TW-I) SCH, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. |  |  | ORD/000289/2022-2023 | 316/CMSD-I | 22/07/2022 | 06/08/2022 | C.M. ENTERPRISE | 3.28 | 3.22 | 98.11 | 1
6 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KALERA W/S SCH (TW-II) SCH, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. |  |  | ORD/000290/2022-2023 | 317/CMSD-I | 22/07/2022 | 06/08/2022 | C.M. ENTERPRISE | 3.28 | 3.12 | 94.91 | 1
7 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT KELERA W/S (TW-I) SCHEME, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. |  |  | ORD/000287/2022-2023 | 320/CMSD-I | 21/07/2022 | 05/08/2022 | C.M. ENTERPRISE | 1.88 | 1.19 | 63.31 | 1
8 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | Additional Transportation of Departmental rig unit no. Super RR with compressor and pump unit from Kalera PWSS under CDD, PHE dte. | Driller In Charge | Junior Engineer | ORD/000307/2022-2023 | 532/CMSD-II(D) | 01/12/2022 | 08/12/2022 | PADMA ENGINEERING & CO. | 0.75 | 0.75 | 100 | 1
9 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | Providing drilling crews for construction of TW (250mm x 150mm) by Departmental rig machine for kalera WS (TW-II), Jamalpur block purba Burdwan, CDD, PHE Dte. |  |  | ORD/000308/2022-2023 | 330/CMSD-I(D) | 15/07/2022 | 30/07/2022 | C.M. ENTERPRISE | 1.74 | 1.38 | 79.17 | 1
10 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT KALERA W/S SCH (TW-II) SCH, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. |  |  | ORD/000292/2022-2023 | 331/CMSD-I | 15/07/2022 | 30/07/2022 | C.M. ENTERPRISE | 1.88 | 1.16 | 61.57 | 1
11 | PURBA BARDHAMAN | Jamalpur | Burdwan Division | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | Material Requisition To Resource Division |  |  | RTOR000118/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 12.9 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Jamalpur | Central Mechanical | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | New Service Connection Charges for Kalera W/S Scheme PH-1 |  |  | BILL/00002/2022-2023 | 25 | 02/01/2023 | 02/01/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.51 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Jamalpur | Central Mechanical | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | New Service Connection Charges for Kalera W/S Scheme PH-2 |  |  | BILL/00003/2022-2023 | 26 | 02/01/2023 | 02/01/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.9 | 0 | 0 | 0
14 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | Hiring of Diesel driven motor cab (BS-III & above) having contract carriage permit along with driver for the office of the Executive Engineer, CDD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 45/S&WSD | 26/04/2023 | 03/05/2023 | ASHUTOSH DAS & CO | 0.87 | 1.69 | 193.47 | 83
Total | [13 empty] | 69.79 | 32.72 | 46.89