## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Jamalpur | Burdwan Division | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | Material Requisition To Resource Division |  |  | RTOR000053/2022-2023 | 5522/BWDQ | 23/12/2022 | 23/12/2022 | Resource Division | 8.88 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Jamalpur | Central Mechanical | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 at Kalera Water Supply Scheme [ Block- Jamalpur ] under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000609/2022-2023 | 3115/CMD | 23/11/2022 | 23/12/2022 | P.K. ENGINEERING | 11.07 | 10.73 | 96.94 | 80
3 | PURBA BARDHAMAN | Jamalpur | Central Mechanical | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-2 at Kalera Water Supply Scheme [ Block- Jamalpur ] under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000610/2022-2023 | 3116/CMD | 23/11/2022 | 23/12/2022 | DUTTA ENTERPRISE | 11.08 | 7.74 | 69.84 | 80
4 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY DEPARTMENTAL RIG MACHINE FOR KALERA W/S (TW-I) SCH, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. |  |  | ORD/000288/2022-2023 | 319/CMSD-I | 21/07/2022 | 05/08/2022 | C.M. ENTERPRISE | 1.74 | 1.74 | 100 | 1
5 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KALERA W/S (TW-I) SCH, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. |  |  | ORD/000289/2022-2023 | 316/CMSD-I | 22/07/2022 | 06/08/2022 | C.M. ENTERPRISE | 3.28 | 3.22 | 98.11 | 1
6 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KALERA W/S SCH (TW-II) SCH, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. |  |  | ORD/000290/2022-2023 | 317/CMSD-I | 22/07/2022 | 06/08/2022 | C.M. ENTERPRISE | 3.28 | 3.12 | 94.91 | 1
7 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT KELERA W/S (TW-I) SCHEME, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. |  |  | ORD/000287/2022-2023 | 320/CMSD-I | 21/07/2022 | 05/08/2022 | C.M. ENTERPRISE | 1.88 | 1.19 | 63.31 | 1
8 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | Additional Transportation of Departmental rig unit no. Super RR with compressor and pump unit from Kalera PWSS under CDD, PHE dte. | Driller In Charge | Junior Engineer | ORD/000307/2022-2023 | 532/CMSD-II(D) | 01/12/2022 | 08/12/2022 | PADMA ENGINEERING & CO. | 0.75 | 0.75 | 100 | 1
9 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | Providing drilling crews for construction of TW (250mm x 150mm) by Departmental rig machine for kalera WS (TW-II), Jamalpur block purba Burdwan, CDD, PHE Dte. |  |  | ORD/000308/2022-2023 | 330/CMSD-I(D) | 15/07/2022 | 30/07/2022 | C.M. ENTERPRISE | 1.74 | 1.38 | 79.17 | 1
10 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT KALERA W/S SCH (TW-II) SCH, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. |  |  | ORD/000292/2022-2023 | 331/CMSD-I | 15/07/2022 | 30/07/2022 | C.M. ENTERPRISE | 1.88 | 1.16 | 61.57 | 1
11 | PURBA BARDHAMAN | Jamalpur | Burdwan Division | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | Material Requisition To Resource Division |  |  | RTOR000118/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 12.9 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Jamalpur | Central Mechanical | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | New Service Connection Charges for Kalera W/S Scheme PH-1 |  |  | BILL/00002/2022-2023 | 25 | 02/01/2023 | 02/01/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.51 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Jamalpur | Central Mechanical | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | New Service Connection Charges for Kalera W/S Scheme PH-2 |  |  | BILL/00003/2022-2023 | 26 | 02/01/2023 | 02/01/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.9 | 0 | 0 | 0
14 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | Hiring of Diesel driven motor cab (BS-III & above) having contract carriage permit along with driver for the office of the Executive Engineer, CDD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 45/S&WSD | 26/04/2023 | 03/05/2023 | ASHUTOSH DAS & CO | 0.87 | 1.69 | 193.47 | 83
15 | PURBA BARDHAMAN | Jamalpur | Burdwan Division | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11491 | New | Augmentation of KALERA Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 350 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation including construction of switch-rooms(5.40mx3.6m) & Boundary walls for new TW site under Jamalpur Block, District:- Purba-Burdwan. [Treated as "New Scheme in place of Augmentation" vide Corrigendum Notice No. 1544/CC, dated 02.08.2022.] | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000256/2022-2023 | 3855/BWD | 07/09/2022 | 31/12/2024 | M/S MAA TARA CONSTRUCTION | 302.71 | 262.2 | 86.62 | 100
Total | [13 empty] | 372.5 | 294.92 | 79.17