## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. | SM/11514 | School | Material Requisition To Resource Division |  |  | RTOR000048/2022-2023 | 5400/BWD | 12/12/2022 | 12/12/2022 | Resource Division | 105.18 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. | SM/11514 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Ketugram - II Block (09 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000362/2022-2023 | 3807/BWD | 02/09/2022 | 02/10/2022 | M/S STANDARD CONSTRUCTION | 9.76 | 7.37 | 75.43 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. | SM/11514 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Katwa I Block (35 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte.(Part-A). | Assistant Engineer |  | ORD/000280/2022-2023 | 3587/BWD | 17/08/2022 | 01/10/2022 | HAMID SK | 38.97 | 33.15 | 85.08 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. | SM/11514 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Katwa I Block (35 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte.(Part B). | Assistant Engineer |  | ORD/000305/2022-2023 | 3635/BWD | 23/08/2022 | 07/10/2022 | JAI MAA DURGA & CO. | 39.46 | 36.01 | 91.26 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. | SM/11514 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Ketugram - I Block (33 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-A). | Assistant Engineer |  | ORD/000266/2022-2023 | 3514/BWD | 12/08/2022 | 26/09/2022 | JAHAR GHOSH | 36.83 | 33.55 | 91.1 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. | SM/11514 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Mongalkote Block (39 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte.(Part-A). | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000267/2022-2023 | 3515/BWD | 12/08/2022 | 26/09/2022 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 43.97 | 39.72 | 90.35 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. | SM/11514 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Mongalkote Block (39 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte.(Part-B). | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000268/2022-2023 | 3516/BWD | 12/08/2022 | 26/09/2022 | S.S. CONSTRUCTION | 43.97 | 39.18 | 89.11 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. | SM/11514 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Ketugram - I Block (33 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-B)._2ND CALL. | Assistant Engineer |  | ORD/000278/2022-2023 | 3586/BWD | 17/08/2022 | 01/10/2022 | ANIRUDDHA FARUQUE | 35.94 | 34.06 | 94.77 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. | SM/11514 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Katwa ? II Block (27 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000277/2022-2023 | 3526/BWD | 12/08/2022 | 26/09/2022 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 30.2 | 24.5 | 81.12 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. | SM/11514 | School | Material Requisition To Resource Division |  |  | RTOR000024/2022-2023 | 3301/BWD | 29/07/2022 | 29/07/2022 | Resource Division | 32.5 | 0 | 0 | 0
Total | [13 empty] | 416.78 | 247.54 | 59.39