## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. | SM/11993 | Support-M&E | Preparation & Submission of DPR for New Water Supply Scheme under JAMALPUR Development Block under Burdwan Division, P.H.E. Dte. [Gr. A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000463/2022-2023 | 3901/BWD | 08/09/2022 | 23/10/2022 | APEX ENGINEERING | 8.83 | 6.18 | 70 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. | SM/11993 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Mongalkote Dev. Block under Katwa Sub-Division under Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000488/2022-2023 | 3931/BWD | 09/09/2022 | 08/11/2022 | RUDRABHISHEK ENTERPRISES LIMITED | 90 | 88.45 | 98.28 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. | SM/11993 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW, PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Burdwan II, Khandaghosh, Memari I & Raina II Dev. Block, under Burdwan Sub-Division under Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000472/2022-2023 | 3841/BWD | 05/09/2022 | 04/11/2022 | MARS PLANNING AND ENGINEERING SERVICES PVT LTD. | 300 | 270.91 | 90.3 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. | SM/11993 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Kalna I & Monteswar Dev. Block under Kalna Sub-Division under Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000487/2022-2023 | 3956/BWD | 09/09/2022 | 08/11/2022 | VENKATESHWARA ENTERPRISES | 180 | 179.89 | 99.94 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. | SM/11993 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW, PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Ausgram II, Galsi I & Bhatar Dev. Block under Durgapur (Burdwan North) Sub-Division under Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000471/2022-2023 | 3825/BWD | 02/09/2022 | 01/11/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 225 | 221.17 | 98.3 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. | SM/11993 | Support-M&E | Preparation & Submission of DPR for New Water Supply Scheme under KETUGRAM - I Development Block under Burdwan Division, P.H.E. Dte. [Gr. A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000511/2022-2023 | 3972/BWD | 13/09/2022 | 28/10/2022 | ENVIROTECH SOLUTIONS | 60.07 | 54.11 | 90.08 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. | SM/11993 | Support-M&E | Preparation & Submission of DPR for New Water Supply Scheme under KETUGRAM - II Development Block under Burdwan Division, P.H.E. Dte. [Gr. B] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000512/2022-2023 | 3988/BWD | 13/09/2022 | 28/10/2022 | ENVIROTECH SOLUTIONS | 30.03 | 26.56 | 88.44 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. | SM/11993 | Support-M&E | Preparation & Submission of DPR for New Water Supply Scheme under PURBASTHALI - I Development Block under Burdwan Division, P.H.E. Dte. [Gr. C] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000513/2022-2023 | 4056/BWD | 15/09/2022 | 30/10/2022 | ECO CARE | 60.07 | 60.04 | 99.96 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. | SM/11993 | Support-M&E | Preparation & Submission of DPR for New Water Supply Scheme under PURBASTHALI - II Development Block under Burdwan Division, P.H.E. Dte. [Gr. D] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000514/2022-2023 | 4079/BWD | 16/09/2022 | 31/10/2022 | ECO CARE | 6.76 | 5.56 | 82.21 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. | SM/11993 | Support-M&E | Continuation Work for Preparation & Submission of DPR for New Water Supply Scheme under KETUGRAM - I Development Block under Burdwan Division, P.H.E. Dte. |  |  | ORD/000920/2022-2023 | 4636/BWD | 17/10/2022 | 01/12/2022 | ENVIROTECH SOLUTIONS | 17.27 | 17.17 | 99.39 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. | SM/11993 | Support-M&E | Work Order for Service for land acquisition for different PWSS under JJM of Purbasthali-I block under Kalna Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000341/2023-2024 | 519/KSD | 06/06/2023 | 06/06/2024 | PARTHA PRATIM ACHARYA | 0.81 | 0.81 | 100 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. | SM/11993 | Support-M&E | Work Order for Service for land acquisition for different PWSS under JJM of Monteswar block under Kalna Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000343/2023-2024 | 535/KSD | 07/06/2023 | 07/06/2024 | PARTHA PRATIM ACHARYA | 0.81 | 0.33 | 40 | 42
Total | [13 empty] | 979.65 | 931.17 | 95.05