## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PHASE-II BY AREA OF KASIARA PIPED WATER SUPPLY SCHEME AT MONGALKOTE BLOCK UNDER BURDWAN DIVISION PHE DTE. | SM/12080 | Retrofitting | Connection of CGWB Tube well Raising Main Line of Head Work Site of Kashiyara Piped Water Supply Scheme within Katwa Sub-Division under Burdwan Division, P.H.E. Dte. (Sl No-1) | Assistant Engineer |  | ORD/000162/2021-2022 | 635/KTS | 20/09/2021 | 05/10/2021 | ASMA ENTERPRISE | 0.92 | 0.94 | 101.91 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PHASE-II BY AREA OF KASIARA PIPED WATER SUPPLY SCHEME AT MONGALKOTE BLOCK UNDER BURDWAN DIVISION PHE DTE. | SM/12080 | Retrofitting | Extention of pipe line for providing FHTC from existing Distribuation System within scheme jurisdiction in Kashiara Piped Water Supply Scheme at Gotishta Village within Katwa Sub-Division under Burdwan Division PHE Dte. (Sl -3) | Assistant Engineer |  | ORD/000160/2021-2022 | 663/KTS | 28/09/2021 | 13/10/2021 | MAJUMDER ENTERPRISE | 4.84 | 4.81 | 99.29 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PHASE-II BY AREA OF KASIARA PIPED WATER SUPPLY SCHEME AT MONGALKOTE BLOCK UNDER BURDWAN DIVISION PHE DTE. | SM/12080 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Gopalbera village under KASIYARA PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl - 1] | Assistant Engineer |  | ORD/000158/2021-2022 | 661/KTS | 28/09/2021 | 13/10/2021 | MAJUMDER ENTERPRISE | 1.26 | 1.23 | 98.37 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PHASE-II BY AREA OF KASIARA PIPED WATER SUPPLY SCHEME AT MONGALKOTE BLOCK UNDER BURDWAN DIVISION PHE DTE. | SM/12080 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Kasiyara and Dirghyasoya village under KASIYARA PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl - 2] | Assistant Engineer |  | ORD/000159/2021-2022 | 662/KTS | 28/09/2021 | 13/10/2021 | MAJUMDER ENTERPRISE | 4.56 | 4.56 | 99.88 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PHASE-II BY AREA OF KASIARA PIPED WATER SUPPLY SCHEME AT MONGALKOTE BLOCK UNDER BURDWAN DIVISION PHE DTE. | SM/12080 | Retrofitting | Providing Functional Household Tap Connection at Gopalbera , Gotistha, dirghesoa habitation of Gopalbera , Gotistha, Kashiara village of Chanak and Gotistha G.P. from existing distribution system within the command area of Kashiara PWSS under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-01) | Assistant Engineer |  | ORD/000590/2021-2022 | 127/KTS | 21/02/2022 | 23/03/2022 | TAPAS KUMAR ROY | 4.83 | 4.73 | 97.93 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PHASE-II BY AREA OF KASIARA PIPED WATER SUPPLY SCHEME AT MONGALKOTE BLOCK UNDER BURDWAN DIVISION PHE DTE. | SM/12080 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Chanak village under Kashiara PWSS under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. _2nd Call [Sl No-01] | Assistant Engineer |  | ORD/000076/2022-2023 | 319/KTS | 25/04/2022 | 16/05/2022 | ASMA ENTERPRISE | 0.95 | 0.92 | 96.62 | 1
Total | [13 empty] | 17.36 | 17.18 | 99