## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BY RETROFITTING (PHASE III) AT KALYANBATI, NARAYANPUR,RADHKRISHNAPUR & SUDPUR MOUZAS WITHIN THE COMMAND AREA OF SUDPUR PIPED WATER SUPPLY SCHEME AND AT KATWA-I BLOCK UNDER KATWA SUB DIVISION WITHIN BUR | SM/12081 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SUDPUR Piped Water Supply Scheme (PART-A) at Katwa-I Block under Burdwan Division, PHE Dte. [Agreement No. 44/2020-2021 OF SE/CC/PHE. DTE.] | Assistant Engineer |  | ORD/000058/2020-2021 | 4290/BWD | 03/11/2020 | 01/02/2021 | MD HASIN | 86.85 | 15.21 | 17.52 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BY RETROFITTING (PHASE III) AT KALYANBATI, NARAYANPUR,RADHKRISHNAPUR & SUDPUR MOUZAS WITHIN THE COMMAND AREA OF SUDPUR PIPED WATER SUPPLY SCHEME AND AT KATWA-I BLOCK UNDER KATWA SUB DIVISION WITHIN BUR | SM/12081 | Retrofitting | Supply, delivery & installation of submersible pumping machinery, voltage stabiliser, chlorinator and internal house wiring for Tube well No.-3 of Sudpur water supply scheme under CMD PHE Dte. |  |  | VCH/000758/2022-2023 | 788/DW/22-23 | 23/11/2022 | 23/11/2022 | M.S. ENTERPRISE | 9.43 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BY RETROFITTING (PHASE III) AT KALYANBATI, NARAYANPUR,RADHKRISHNAPUR & SUDPUR MOUZAS WITHIN THE COMMAND AREA OF SUDPUR PIPED WATER SUPPLY SCHEME AND AT KATWA-I BLOCK UNDER KATWA SUB DIVISION WITHIN BUR | SM/12081 | Retrofitting | Laying of pipe line parallel to the main line of the existing Distribution System including providing FHTC at Kalyanbati, Narayanpur, Bijoynagar, Purba Bijnagar & Ramkrishnapur village (Mouza) within scheme jurisdiction of SUDPUR Piped W/S. Scheme under Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000279/2021-2022 | 6972/BWD | 15/12/2021 | 13/02/2022 | MD HASIN | 63.4 | 13.33 | 21.02 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BY RETROFITTING (PHASE III) AT KALYANBATI, NARAYANPUR,RADHKRISHNAPUR & SUDPUR MOUZAS WITHIN THE COMMAND AREA OF SUDPUR PIPED WATER SUPPLY SCHEME AND AT KATWA-I BLOCK UNDER KATWA SUB DIVISION WITHIN BUR | SM/12081 | Retrofitting | Balance work of OHR at Head Work site, construction of HUME Pipe culvert , Road restoration work and boundary wall at 2nd TW site with Gate, land development at Head work site and 2nd TW site under KAITHAN, SUDPUR & PANUHAT Piped Water Supply Scheme under KATWA -I Block, under Katwa Sub-Division within Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000486/2024-2025 | 3141/BWD | 20/08/2024 | 18/12/2024 | VISHAL CONSTRUCTION CO. | 126.29 | 0 | 0 | 50
5 | PURBA BARDHAMAN |  | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BY RETROFITTING (PHASE III) AT KALYANBATI, NARAYANPUR,RADHKRISHNAPUR & SUDPUR MOUZAS WITHIN THE COMMAND AREA OF SUDPUR PIPED WATER SUPPLY SCHEME AND AT KATWA-I BLOCK UNDER KATWA SUB DIVISION WITHIN BUR | SM/12081 | Retrofitting | Construction of valve Chamber and supply of sluice valve at Sudpur PWSS under Katwa-I Block under Katwa Sub-Division under Burdwan Division, PHE Dte.[Sl No-4] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000372/2023-2024 | 671/KTS | 22/06/2023 | 22/07/2023 | HAMID SK | 0.93 | 0.93 | 100 | 100
Total | [13 empty] | 286.9 | 29.47 | 10.27