## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Laying of pipe line (parallel to the main line) of the existing Distribution System and providing Functional Household Tap connection (FHTC) from existing distribution system within the command area of Srikhanda PWSS at Katwa-I block under Burdwan divisio | SM/12116 | Augmentation | Laying of pipe line (Parallel to the main line) of the existing Distribution System and Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of SRIKHANDA Piped Water Supply Scheme at Katwa-I Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000023/2022-2023 | 2027/BWD | 18/04/2022 | 18/05/2022 | M/S JOY | 53.12 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Laying of pipe line (parallel to the main line) of the existing Distribution System and providing Functional Household Tap connection (FHTC) from existing distribution system within the command area of Srikhanda PWSS at Katwa-I block under Burdwan divisio | SM/12116 | Augmentation | Balance work of OHR, construction Concrete Road, Functional Household Tap Connection, Road restoration etc. for Nanagar PWSS, Srikhanda PWSS, under KATWA -I Block under Katwa Sub-Divn under Burdwan Division, PHE Dte. District:- Purba-Bardhaman. | Assistant Engineer |  | ORD/000685/2024-2025 | 3655/BWD | 21/10/2024 | 18/02/2025 | HAMID SK | 121.69 | 0 | 0 | 0
Total | [13 empty] | 174.81 | 0 | 0