## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC BY RETROFITTING AT AGRADWIP MOUZA WITHIN THE COMMAND AREA AGRADWIP PIPED WATER SUPPLY SCHEME AT KATWA II BLOCK UNDER BURDWAN DIVISION PHE DTE PART B | SM/13043 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AGRADWIP Piped Water Supply Scheme at Agradwip, Babla danga, Gonsaidhowra, Saheb Nagar & Sarawaridhowra (Mouza), Katwa - II Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000445/2021-2022 | 6253/BWD | 01/11/2021 | 31/12/2021 | SHUBHRA KANTI GHOSH | 53.67 | 34.17 | 63.66 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC BY RETROFITTING AT AGRADWIP MOUZA WITHIN THE COMMAND AREA AGRADWIP PIPED WATER SUPPLY SCHEME AT KATWA II BLOCK UNDER BURDWAN DIVISION PHE DTE PART B | SM/13043 | Retrofitting | Providing Functional Household Tap Connection from existing distribution system within the command area of AGRADWIP PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-1) | Assistant Engineer |  | ORD/000237/2021-2022 | 688/KTS | 08/10/2021 | 15/10/2021 | CHANCHAL PAL | 1.21 | 1.2 | 99.58 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC BY RETROFITTING AT AGRADWIP MOUZA WITHIN THE COMMAND AREA AGRADWIP PIPED WATER SUPPLY SCHEME AT KATWA II BLOCK UNDER BURDWAN DIVISION PHE DTE PART B | SM/13043 | Retrofitting | Extension of pipe line of Providing Functional Household Tap Connection (FHTC) from existing distribution system within command area of Agradwip Water Supply Schame under Agradwip PWSS at Gonsaishowra, & Sarawaridhowar Habitation Katwa-II Block Katwa Sub-Division under Burdwan Division PHE Dte.. [Sl No-05] | Assistant Engineer |  | ORD/000608/2021-2022 | 172/KTS | 25/02/2022 | 04/03/2022 | SHUBHRA KANTI GHOSH | 1.32 | 1.3 | 98.08 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC BY RETROFITTING AT AGRADWIP MOUZA WITHIN THE COMMAND AREA AGRADWIP PIPED WATER SUPPLY SCHEME AT KATWA II BLOCK UNDER BURDWAN DIVISION PHE DTE PART B | SM/13043 | Retrofitting | Extension of pipe line of Providing Functional Household Tap Connection (FHTC) from existing distribution system within command area of Agradwip Water Supply Schame under Agradwip PWSS at Babla danga and Saheb Nagar Habitation Katwa-II Block Katwa Sub-Division under Burdwan Division PHE Dte.. [Sl No-02] | Assistant Engineer |  | ORD/000605/2021-2022 | 161/KTS | 24/02/2022 | 03/03/2022 | SHUBHRA KANTI GHOSH | 2.1 | 2.08 | 99 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC BY RETROFITTING AT AGRADWIP MOUZA WITHIN THE COMMAND AREA AGRADWIP PIPED WATER SUPPLY SCHEME AT KATWA II BLOCK UNDER BURDWAN DIVISION PHE DTE PART B | SM/13043 | Retrofitting | Supplying and laying of valves along with construction of valve chamber at the existing distribution pipe line of Agradwip PWSS under Katwa Sub-Division under Burdwan Division, PHE Dte [Sl No-04] | Assistant Engineer |  | ORD/000157/2022-2023 | 440/KTS | 27/06/2022 | 27/07/2022 | TAPAS KUMAR ROY | 0.78 | 0.78 | 100 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC BY RETROFITTING AT AGRADWIP MOUZA WITHIN THE COMMAND AREA AGRADWIP PIPED WATER SUPPLY SCHEME AT KATWA II BLOCK UNDER BURDWAN DIVISION PHE DTE PART B | SM/13043 | Retrofitting | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme AGRADWIP, KHETPUR PALASHI, SAHAPUR PWSS (Sl No-1) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000069/2023-2024 | 393/KTS | 13/04/2023 | 13/05/2023 | SIRCON ENGINEERING SERVICES | 3.71 | 1.24 | 33.33 | 100
Total | [13 empty] | 62.79 | 40.76 | 64.91