## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Kusha Piped Water Supply Scheme | SM/13279 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of Assistant Engineer, under C.M.D. P.H.E. Dte. w.e.f.-01/07/2023 to 31/08/2023. [Under JJM Works]. | ASSISTANT ENGINEER | Junior Engineer | ORD/000321/2023-2024 | 523/A/CMSD-I | 28/06/2023 | 29/08/2023 | SUBRATA BHADRA | 0.79 | 0.76 | 95.9 | 50
2 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Kusha Piped Water Supply Scheme | SM/13279 | New | KUSHA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Bardhaman-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000671/2022-2023 | 389/BWD. | 31/01/2023 | 01/04/2025 | SYED KHORSED ALAM | 250.51 | 234.57 | 93.64 | 75
3 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Kusha Piped Water Supply Scheme | SM/13279 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kusha Water Supply Scheme [Block- Burdwan-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000034/2023-2024 | 2470/CMD | 30/05/2023 | 29/06/2023 | SUBRATA BHADRA | 28.71 | 23.98 | 83.52 | 60
4 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Kusha Piped Water Supply Scheme | SM/13279 | New | Additional laying distribution system work for KUSHA W/S. Scheme under Burdwan - II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000434/2023-2024 | 3386/BWD | 03/08/2023 | 02/10/2023 | RICK CONSTRUCTION | 39.84 | 39.84 | 100 | 100
5 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Kusha Piped Water Supply Scheme | SM/13279 | New | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 2.48 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Kusha Piped Water Supply Scheme | SM/13279 | New | Material Requisition To Resource Division |  |  | RTOR000069/2022-2023 | 1250/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 6.52 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Kusha Piped Water Supply Scheme | SM/13279 | New | Material Requisition To Resource Division |  |  | RTOR000726/2023-2024 | 5270/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 21.07 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Kusha Piped Water Supply Scheme | SM/13279 | New | New Service connection charges for Kusha W/S Scheme TW-I |  |  | BILL/00573/2023-2024 | BP-2023-24-9 | 12/05/2023 | 12/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.07 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Kusha Piped Water Supply Scheme | SM/13279 | New | New Service connection charges for Kusha W/S Scheme TW-II |  |  | BILL/00574/2023-2024 | BP-2023-24-10 | 12/05/2023 | 12/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.41 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Kusha Piped Water Supply Scheme | SM/13279 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 31/10/2024 | DILIP MAHATO | 53.14 | 0 | 0 | 12
11 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Kusha Piped Water Supply Scheme | SM/13279 | New | Supply & delivery of standby Submersible pumping machinery & automatic Chlorinator for Kusha & others water supply scheme, under CMD, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/001412/2023-2024 | 150/CMSD | 22/01/2024 | 06/02/2024 | SUBRATA BHADRA | 1.76 | 1.76 | 100 | 100
12 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Kusha Piped Water Supply Scheme | SM/13279 | New | Designing, making and erection of Sign Board for SWAJAL GRAM in Korar village of Burdwan-II Block under Kusha Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte (5 nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000612/2025-2026 | 2356/BSD | 21/08/2025 | 31/08/2025 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.72 | 0 | 0 | 100
Total | [13 empty] | 415.03 | 300.91 | 72.5